## SupplyPro Orders
Builder Name | Subdivision | Lot / Block | Task | Requested Start Date | Actual Start Date | Subtotal | Tax | Total | Contact Name | Contact Phone | Contact Email | Status
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0004 | Frame Punch /Tyvek 2 [10001 -20081367 -000] [OP] | 4/1/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0007 | Windows [10001 -20103722 -000] [OP] | 4/1/2026 |  | $7,086.69 | $0.00 | $7,086.69 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0191 | Deliver Frame Package [10001 -20103215 -009] [OH] | 4/3/2026 |  | $781.81 | $0.00 | $781.81 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0191 | Deliver Frame Package [10001 -20103133 -000] [OP] | 4/3/2026 |  | $33,630.74 | $0.00 | $33,630.74 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 40s | 0459 | Screens | 4/6/2026 |  | $0.00 | $0.00 | $0.00 | Kyle zzzSalisbury | (000) 000-1122 | kyle.salisbury@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0191 | Framing Labor-Draw 1 [10001 -20103134 -000] [OP] | 4/6/2026 |  | $11,932.70 | $0.00 | $11,932.70 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0191 | Framing Labor-Draw 1 [10001 -20103215 -009] [OH] | 4/6/2026 |  | $355.20 | $0.00 | $355.20 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0047 | Framing Labor-Draw 1 [10001 -20115809 -000] [OP] | 4/6/2026 |  | $12,360.10 | $0.00 | $12,360.10 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0145 | White Sheet Framing [10001 -20093692 -000] [OP] | 4/6/2026 |  | $1.00 | $0.00 | $1.00 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0191 | Deliver Frame Package [10001 -20164676 -000] [OC] | 4/6/2026 |  | ($3,602.00) | $0.00 | ($3,602.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0192 | Deliver Frame Package [10001 -20164677 -000] [OC] | 4/6/2026 |  | ($4,366.00) | $0.00 | ($4,366.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0011 | Deliver Frame Package [10001 -20164691 -000] [OC] | 4/6/2026 |  | $0.00 | $0.00 | $0.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0002 | Deliver Frame Package [10001 -20164680 -000] [OC] | 4/6/2026 |  | ($2,817.00) | $0.00 | ($2,817.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0003 | Deliver Frame Package [10001 -20164681 -000] [OC] | 4/6/2026 |  | ($2,760.00) | $0.00 | ($2,760.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0004 | Deliver Frame Package [10001 -20164682 -000] [OC] | 4/6/2026 |  | ($2,736.00) | $0.00 | ($2,736.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0005 | Deliver Frame Package [10001 -20164683 -000] [OC] | 4/6/2026 |  | ($2,669.00) | $0.00 | ($2,669.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0006 | Deliver Frame Package [10001 -20164684 -000] [OC] | 4/6/2026 |  | ($4,158.00) | $0.00 | ($4,158.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0008 | Frame Punch /Tyvek 2 [10001 -20081581 -000] [OP] | 4/7/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0015 | Framing Labor-Draw 1 [10001 -20122290 -000] [OP] | 4/7/2026 |  | $15,240.50 | $0.00 | $15,240.50 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0127 | Screens | 4/7/2026 |  | $0.00 | $0.00 | $0.00 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0192 | Deliver Frame Package [10001 -20103358 -000] [OP] | 4/8/2026 |  | $35,701.06 | $0.00 | $35,701.06 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0192 | Framing Labor-Draw 1 [10001 -20103359 -000] [OP] | 4/8/2026 |  | $12,450.70 | $0.00 | $12,450.70 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0002 | Deliver Frame Package [10001 -20110014 -000] [OP] | 4/8/2026 |  | $38,300.49 | $0.00 | $38,300.49 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0003 | Deliver Frame Package [10001 -20110125 -000] [OP] | 4/8/2026 |  | $39,154.89 | $0.00 | $39,154.89 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0004 | Deliver Frame Package [10001 -20110231 -000] [OP] | 4/8/2026 |  | $39,656.25 | $0.00 | $39,656.25 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0005 | Deliver Frame Package [10001 -20110334 -000] [OP] | 4/8/2026 |  | $38,637.91 | $0.00 | $38,637.91 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0006 | Deliver Frame Package [10001 -20110438 -000] [OP] | 4/8/2026 |  | $42,480.66 | $0.00 | $42,480.66 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0118 | EPO: Replace front door $1410 [10001 -20144995 -000] [OX] | 4/8/2026 |  | $1,410.00 | $0.00 | $1,410.00 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0192 | Exterior Door TK [10001 -20103363 -000] [OP] | 4/9/2026 |  | $5,629.04 | $0.00 | $5,629.04 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0192 | Windows [10001 -20103364 -000] [OP] | 4/9/2026 |  | $5,850.30 | $0.00 | $5,850.30 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0118 | EPO: Exterior Door $1625 [10001 -20156104 -000] [OX] | 4/9/2026 |  | $1,625.00 | $0.00 | $1,625.00 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0002 | Framing Labor-Draw 1 [10001 -20110016 -000] [OP] | 4/9/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0003 | Framing Labor-Draw 1 [10001 -20110127 -000] [OP] | 4/9/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0004 | Framing Labor-Draw 1 [10001 -20110233 -000] [OP] | 4/9/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0005 | Framing Labor-Draw 1 [10001 -20110336 -000] [OP] | 4/9/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0006 | Framing Labor-Draw 1 [10001 -20110440 -000] [OP] | 4/9/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0010 | Frame Punch /Tyvek 2 [10001 -20049944 -000] [OP] | 4/10/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Signatures | 0238 | EPO: Windows [10001 -20176315 -000] [OC] | 4/10/2026 |  | $505.82 | $0.00 | $505.82 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0011 | Exterior Door TK [10001 -20105205 -000] [OP] | 4/13/2026 |  | $4,309.08 | $0.00 | $4,309.08 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0011 | Windows [10001 -20105206 -000] [OP] | 4/13/2026 |  | $6,429.67 | $0.00 | $6,429.67 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0249 | Exterior Door TK [10001 -20096712 -000] [OP] | 4/13/2026 |  | $3,346.30 | $0.00 | $3,346.30 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0249 | Windows [10001 -20096713 -000] [OP] | 4/13/2026 |  | $4,140.84 | $0.00 | $4,140.84 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0015 | Frame Punch /Tyvek 2 [10001 -20122291 -000] [OP] | 4/13/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0005 | Deliver Frame Package [10001 -20150926 -000] [OP] | 4/13/2026 |  | $32,357.90 | $0.00 | $32,357.90 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0016 | Frame Punch /Tyvek 2 [10001 -20112992 -000] [OP] | 4/14/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0015 | Exterior Door TK [10001 -20122294 -000] [OP] | 4/14/2026 |  | $5,234.54 | $0.00 | $5,234.54 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0015 | Windows [10001 -20122295 -000] [OP] | 4/14/2026 |  | $6,087.24 | $0.00 | $6,087.24 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0005 | Framing Labor-Draw 1 [10001 -20150927 -000] [OP] | 4/14/2026 |  | $16,087.80 | $0.00 | $16,087.80 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0251 | Exterior Door TK [10001 -20106806 -000] [OP] | 4/15/2026 |  | $3,346.30 | $0.00 | $3,346.30 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0251 | Windows [10001 -20106807 -000] [OP] | 4/15/2026 |  | $4,372.36 | $0.00 | $4,372.36 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0193 | Framing Labor-Draw 1 [10001 -20108915 -000] [OP] | 4/15/2026 |  | $14,337.70 | $0.00 | $14,337.70 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0145 | Deliver Frame Package [10001 -20093688 -000] [OP] | 4/16/2026 |  | $33,979.24 | $0.00 | $33,979.24 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0191 | Exterior Door TK [10001 -20103138 -000] [OP] | 4/16/2026 |  | $4,520.56 | $0.00 | $4,520.56 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0191 | Windows [10001 -20103139 -000] [OP] | 4/16/2026 |  | $5,187.44 | $0.00 | $5,187.44 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0011 | Frame Punch /Tyvek 2 [10001 -20105202 -000] [OP] | 4/16/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0118 | Exterior Door TK [10001 -20113256 -000] [OP] | 4/16/2026 |  | $2,924.78 | $0.00 | $2,924.78 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0118 | Windows [10001 -20113257 -000] [OP] | 4/16/2026 |  | $4,187.19 | $0.00 | $4,187.19 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0145 | Deliver Frame Package [10001 -20164674 -000] [OC] | 4/16/2026 |  | ($3,540.00) | $0.00 | ($3,540.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0018 | Screens | 4/16/2026 |  | $0.00 | $0.00 | $0.00 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0168 | EPO: Windows [10001 -20185860 -000] [OC] | 4/16/2026 |  | $206.62 | $0.00 | $206.62 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0012 | Exterior Door TK [10001 -20105345 -000] [OP] | 4/17/2026 |  | $4,520.56 | $0.00 | $4,520.56 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0250 | Exterior Door TK [10001 -20105834 -000] [OP] | 4/17/2026 |  | $3,346.30 | $0.00 | $3,346.30 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0250 | Windows [10001 -20105835 -000] [OP] | 4/17/2026 |  | $5,260.04 | $0.00 | $5,260.04 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0145 | Framing Labor-Draw 1 [10001 -20093689 -000] [OP] | 4/17/2026 |  | $11,932.70 | $0.00 | $11,932.70 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0052 | Screens | 4/17/2026 |  | $0.00 | $0.00 | $0.00 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0039 | Deliver Frame Package [10001 -20146733 -000] [OP] | 4/17/2026 |  | $24,697.73 | $0.00 | $24,697.73 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0153 | Exterior Door TK [10001 -20121682 -000] [OP] | 4/20/2026 |  | $4,268.52 | $0.00 | $4,268.52 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0153 | Windows [10001 -20121683 -000] [OP] | 4/20/2026 |  | $5,689.13 | $0.00 | $5,689.13 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0181 | Screens | 4/20/2026 |  | $0.00 | $0.00 | $0.00 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0009 | Deliver Frame Package [10001 -20166961 -000] [OP] | 4/20/2026 |  | $35,227.73 | $0.00 | $35,227.73 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0039 | Framing Labor-Draw 1 [10001 -20146734 -000] [OP] | 4/20/2026 |  | $10,284.40 | $0.00 | $10,284.40 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0039 | Deliver Frame Package [10001 -20187809 -000] [OC] | 4/20/2026 |  | $1,269.97 | $0.00 | $1,269.97 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0012 | Frame Punch /Tyvek 2 [10001 -20105342 -000] [OP] | 4/21/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0017 | Exterior Door TK [10001 -20113101 -000] [OP] | 4/21/2026 |  | $4,520.56 | $0.00 | $4,520.56 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0017 | Windows [10001 -20113102 -000] [OP] | 4/21/2026 |  | $6,383.72 | $0.00 | $6,383.72 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0193 | Exterior Door TK [10001 -20108919 -000] [OP] | 4/21/2026 |  | $5,487.53 | $0.00 | $5,487.53 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0193 | Windows [10001 -20108920 -000] [OP] | 4/21/2026 |  | $5,444.61 | $0.00 | $5,444.61 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0009 | Framing Labor-Draw 1 [10001 -20166962 -000] [OP] | 4/21/2026 |  | $17,693.60 | $0.00 | $17,693.60 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0018 | Framing Labor-Draw 1 [10001 -20167583 -000] [OP] | 4/21/2026 |  | $16,528.10 | $0.00 | $16,528.10 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0020 | Frame Punch /Tyvek 2 [10001 -20105592 -000] [OP] | 4/21/2026 |  | $540.00 | $0.00 | $540.00 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0013 | Exterior Door TK [10001 -20122192 -000] [OP] | 4/22/2026 |  | $4,099.04 | $0.00 | $4,099.04 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0013 | Windows [10001 -20122193 -000] [OP] | 4/22/2026 |  | $5,985.39 | $0.00 | $5,985.39 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0145 | Exterior Door TK [10001 -20093693 -000] [OP] | 4/23/2026 |  | $4,099.04 | $0.00 | $4,099.04 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Bradshaw Farms Alleys | 0015 | Screens | 4/23/2026 |  | $0.00 | $0.00 | $0.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0191 | Screens | 4/23/2026 |  | $0.00 | $0.00 | $0.00 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0007 | Framing Labor-Draw 1 [10001 -20095928 -000] [OP] | 4/23/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0008 | Framing Labor-Draw 1 [10001 -20096033 -000] [OP] | 4/23/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0009 | Framing Labor-Draw 1 [10001 -20099408 -000] [OP] | 4/23/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0010 | Framing Labor-Draw 1 [10001 -20099511 -000] [OP] | 4/23/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0011 | Framing Labor-Draw 1 [10001 -20102339 -000] [OP] | 4/23/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0012 | Framing Labor-Draw 1 [10001 -20102444 -000] [OP] | 4/23/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0152 | Exterior Door TK [10001 -20123759 -000] [OP] | 4/23/2026 |  | $4,786.42 | $0.00 | $4,786.42 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0152 | Windows [10001 -20123760 -000] [OP] | 4/23/2026 |  | $6,951.73 | $0.00 | $6,951.73 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0190 | Deliver Frame Package [10001 -20054807 -008] [OH] | 4/24/2026 |  | $1,825.04 | $0.00 | $1,825.04 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0190 | Deliver Frame Package [10001 -20103245 -000] [OP] | 4/24/2026 |  | $33,630.74 | $0.00 | $33,630.74 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0017 | Frame Punch /Tyvek 2 [10001 -20113098 -000] [OP] | 4/24/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0190 | Deliver Frame Package [10001 -20164675 -000] [OC] | 4/24/2026 |  | ($3,602.00) | $0.00 | ($3,602.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0001 | Exterior Door TK [10001 -20109690 -000] [OP] | 4/24/2026 |  | $7,049.96 | $0.00 | $7,049.96 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0001 | Windows [10001 -20109691 -000] [OP] | 4/24/2026 |  | $4,430.91 | $0.00 | $4,430.91 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0002 | Exterior Door TK [10001 -20110020 -000] [OP] | 4/24/2026 |  | $6,899.06 | $0.00 | $6,899.06 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0002 | Windows [10001 -20110021 -000] [OP] | 4/24/2026 |  | $4,367.26 | $0.00 | $4,367.26 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0003 | Exterior Door TK [10001 -20110131 -000] [OP] | 4/24/2026 |  | $7,049.96 | $0.00 | $7,049.96 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0003 | Windows [10001 -20110132 -000] [OP] | 4/24/2026 |  | $3,610.16 | $0.00 | $3,610.16 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0004 | Exterior Door TK [10001 -20110237 -000] [OP] | 4/24/2026 |  | $6,899.06 | $0.00 | $6,899.06 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0004 | Windows [10001 -20110238 -000] [OP] | 4/24/2026 |  | $4,256.65 | $0.00 | $4,256.65 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0005 | Exterior Door TK [10001 -20110340 -000] [OP] | 4/24/2026 |  | $7,049.96 | $0.00 | $7,049.96 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0005 | Windows [10001 -20110341 -000] [OP] | 4/24/2026 |  | $3,838.32 | $0.00 | $3,838.32 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0006 | Exterior Door TK [10001 -20110444 -000] [OP] | 4/24/2026 |  | $6,899.06 | $0.00 | $6,899.06 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0006 | Windows [10001 -20110445 -000] [OP] | 4/24/2026 |  | $4,808.47 | $0.00 | $4,808.47 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0026 | Deliver Frame Package [10001 -20167696 -000] [OP] | 4/24/2026 |  | $28,696.31 | $0.00 | $28,696.31 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0145 | Framing Labor-Draw 1 [10001 -20194159 -000] [OC] | 4/24/2026 |  | $247.90 | $0.00 | $247.90 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Tulip Hills Townhome | 0194 | EPO: Framing Labor-Draw 1 [10001 -20202812 -000] [OC] | 4/24/2026 |  | ($200.00) | $0.00 | ($200.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0190 | Framing Labor-Draw 1 [10001 -20103246 -000] [OP] | 4/27/2026 |  | $11,932.70 | $0.00 | $11,932.70 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0190 | Framing Labor-Draw 1 [10001 -20054808 -008] [OH] | 4/27/2026 |  | $518.00 | $0.00 | $518.00 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0013 | Frame Punch /Tyvek 2 [10001 -20122189 -000] [OP] | 4/27/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0014 | Exterior Door TK [10001 -20151709 -000] [OP] | 4/27/2026 |  | $4,916.91 | $0.00 | $4,916.91 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0014 | Windows [10001 -20151710 -000] [OP] | 4/27/2026 |  | $7,246.97 | $0.00 | $7,246.97 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0005 | Frame Punch /Tyvek 2 [10001 -20150928 -000] [OP] | 4/27/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0018 | Exterior Door TK [10001 -20167587 -000] [OP] | 4/27/2026 |  | $4,711.49 | $0.00 | $4,711.49 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0018 | Windows [10001 -20167588 -000] [OP] | 4/27/2026 |  | $11,731.01 | $0.00 | $11,731.01 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0040 | Deliver Frame Package [10001 -20166574 -000] [OP] | 4/27/2026 |  | $24,670.20 | $0.00 | $24,670.20 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0026 | Framing Labor-Draw 1 [10001 -20167697 -000] [OP] | 4/27/2026 |  | $12,434.10 | $0.00 | $12,434.10 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0047 | Exterior Door TK [10001 -20115813 -000] [OP] | 4/28/2026 |  | $3,306.62 | $0.00 | $3,306.62 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0047 | Windows [10001 -20115814 -000] [OP] | 4/28/2026 |  | $4,576.24 | $0.00 | $4,576.24 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0047 | Frame Punch /Tyvek 2 [10001 -20115810 -000] [OP] | 4/28/2026 |  | $540.00 | $0.00 | $540.00 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0005 | Exterior Door TK [10001 -20150931 -000] [OP] | 4/28/2026 |  | $4,520.56 | $0.00 | $4,520.56 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0005 | Windows [10001 -20150932 -000] [OP] | 4/28/2026 |  | $7,402.50 | $0.00 | $7,402.50 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0040 | Framing Labor-Draw 1 [10001 -20166575 -000] [OP] | 4/28/2026 |  | $9,740.50 | $0.00 | $9,740.50 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Bradshaw Farms Alleys | 0024 | Exterior Door TK [10001 -20125744 -000] [OP] | 4/30/2026 |  | $4,383.36 | $58.65 | $4,442.01 | Cynthia Zubia | (615) 887-2898 | cynthia.zubia@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Bradshaw Farms Alleys | 0024 | Windows [10001 -20125745 -000] [OP] | 4/30/2026 |  | $5,687.51 | $0.00 | $5,687.51 | Cynthia Zubia | (615) 887-2898 | cynthia.zubia@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0014 | Frame Punch /Tyvek 2 [10001 -20151706 -000] [OP] | 4/30/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0177 | Screens | 4/30/2026 |  | $0.00 | $0.00 | $0.00 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0110 | Exterior Door TK [10001 -20135814 -000] [OP] | 4/30/2026 |  | $3,405.83 | $0.00 | $3,405.83 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0110 | Windows [10001 -20135815 -000] [OP] | 4/30/2026 |  | $3,972.73 | $0.00 | $3,972.73 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0255 | Exterior Door TK [10001 -20146308 -000] [OP] | 4/30/2026 |  | $3,346.30 | $0.00 | $3,346.30 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0255 | Windows [10001 -20146309 -000] [OP] | 4/30/2026 |  | $5,425.79 | $0.00 | $5,425.79 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0039 | Exterior Door TK [10001 -20146738 -000] [OP] | 4/30/2026 |  | $5,570.52 | $0.00 | $5,570.52 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0039 | Windows [10001 -20146739 -000] [OP] | 4/30/2026 |  | $5,252.40 | $0.00 | $5,252.40 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0159 | Exterior Door TK [10001 -20152923 -000] [OP] | 4/30/2026 |  | $4,649.26 | $0.00 | $4,649.26 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0159 | Windows [10001 -20152924 -000] [OP] | 4/30/2026 |  | $8,326.01 | $0.00 | $8,326.01 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0252 | Exterior Door TK [10001 -20146131 -000] [OP] | 4/30/2026 |  | $4,223.70 | $0.00 | $4,223.70 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0252 | Windows [10001 -20146132 -000] [OP] | 4/30/2026 |  | $4,116.24 | $0.00 | $4,116.24 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0309 | Exterior Door TK [10001 -20124108 -000] [OP] | 4/30/2026 |  | $3,585.17 | $0.00 | $3,585.17 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0309 | Windows [10001 -20124109 -000] [OP] | 4/30/2026 |  | $4,408.16 | $0.00 | $4,408.16 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0310 | Exterior Door TK [10001 -20123880 -000] [OP] | 4/30/2026 |  | $4,006.69 | $0.00 | $4,006.69 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0310 | Windows [10001 -20123881 -000] [OP] | 4/30/2026 |  | $4,065.74 | $0.00 | $4,065.74 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0308 | Exterior Door TK [10001 -20124329 -000] [OP] | 4/30/2026 |  | $4,006.69 | $0.00 | $4,006.69 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0308 | Windows [10001 -20124330 -000] [OP] | 4/30/2026 |  | $5,084.80 | $0.00 | $5,084.80 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0311 | Exterior Door TK [10001 -20124222 -000] [OP] | 4/30/2026 |  | $3,585.17 | $0.00 | $3,585.17 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0311 | Windows [10001 -20124223 -000] [OP] | 4/30/2026 |  | $4,408.16 | $0.00 | $4,408.16 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0312 | Exterior Door TK [10001 -20124575 -000] [OP] | 4/30/2026 |  | $4,006.69 | $0.00 | $4,006.69 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0312 | Windows [10001 -20124576 -000] [OP] | 4/30/2026 |  | $4,065.74 | $0.00 | $4,065.74 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0313 | Exterior Door TK [10001 -20124472 -000] [OP] | 4/30/2026 |  | $4,006.69 | $0.00 | $4,006.69 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0313 | Windows [10001 -20124473 -000] [OP] | 4/30/2026 |  | $5,084.80 | $0.00 | $5,084.80 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 40s | 0272 | Screens | 4/30/2026 |  | $0.00 | $0.00 | $0.00 | Kyle zzzSalisbury | (000) 000-1122 | kyle.salisbury@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0111 | Exterior Door TK [10001 -20105732 -000] [OP] | 5/1/2026 |  | $3,742.65 | $0.00 | $3,742.65 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0111 | Windows [10001 -20105733 -000] [OP] | 5/1/2026 |  | $5,260.04 | $0.00 | $5,260.04 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0113 | Exterior Door TK [10001 -20106963 -000] [OP] | 5/1/2026 |  | $3,742.65 | $0.00 | $3,742.65 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0113 | Windows [10001 -20106964 -000] [OP] | 5/1/2026 |  | $5,425.79 | $0.00 | $5,425.79 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0008 | Windows [10001 -20096038 -000] [OP] | 5/1/2026 |  | $5,182.87 | $0.00 | $5,182.87 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0009 | Windows [10001 -20099413 -000] [OP] | 5/1/2026 |  | $3,846.84 | $0.00 | $3,846.84 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0010 | Windows [10001 -20099516 -000] [OP] | 5/1/2026 |  | $5,182.87 | $0.00 | $5,182.87 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0011 | Windows [10001 -20102344 -000] [OP] | 5/1/2026 |  | $3,846.84 | $0.00 | $3,846.84 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0012 | Windows [10001 -20102449 -000] [OP] | 5/1/2026 |  | $5,555.78 | $0.00 | $5,555.78 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0114 | Exterior Door TK [10001 -20111840 -000] [OP] | 5/1/2026 |  | $2,924.78 | $0.00 | $2,924.78 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0114 | Windows [10001 -20111841 -000] [OP] | 5/1/2026 |  | $4,187.19 | $0.00 | $4,187.19 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0009 | Exterior Door TK [10001 -20166966 -000] [OP] | 5/1/2026 |  | $4,711.49 | $0.00 | $4,711.49 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0009 | Windows [10001 -20166967 -000] [OP] | 5/1/2026 |  | $11,323.51 | $0.00 | $11,323.51 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Mill at McFarlin 40s | 0018 | Frame Punch /Tyvek 2 [10001 -20167584 -000] [OP] | 5/1/2026 |  | $540.00 | $0.00 | $540.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0041 | Deliver Frame Package [10001 -20168333 -000] [OP] | 5/1/2026 |  | $24,947.11 | $0.00 | $24,947.11 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0001 | Deliver Frame Package [10001 -20109684 -000] [OP] | 5/4/2026 |  | $42,951.18 | $0.00 | $42,951.18 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0008 | Exterior Door TK [10001 -20096037 -000] [OP] | 5/4/2026 |  | $5,168.11 | $0.00 | $5,168.11 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0009 | Exterior Door TK [10001 -20099412 -000] [OP] | 5/4/2026 |  | $5,168.11 | $0.00 | $5,168.11 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0010 | Exterior Door TK [10001 -20099515 -000] [OP] | 5/4/2026 |  | $5,168.11 | $0.00 | $5,168.11 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0011 | Exterior Door TK [10001 -20102343 -000] [OP] | 5/4/2026 |  | $5,168.11 | $0.00 | $5,168.11 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0012 | Exterior Door TK [10001 -20102448 -000] [OP] | 5/4/2026 |  | $5,168.11 | $0.00 | $5,168.11 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0001 | Deliver Frame Package [10001 -20164679 -000] [OC] | 5/4/2026 |  | ($4,130.00) | $0.00 | ($4,130.00) | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0081 | Exterior Door TK [10001 -20146635 -000] [OP] | 5/4/2026 |  | $5,234.54 | $0.00 | $5,234.54 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0081 | Windows [10001 -20146636 -000] [OP] | 5/4/2026 |  | $8,629.67 | $0.00 | $8,629.67 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0041 | Framing Labor-Draw 1 [10001 -20168334 -000] [OP] | 5/4/2026 |  | $10,630.30 | $0.00 | $10,630.30 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0190 | Exterior Door TK [10001 -20054809 -008] [OH] | 5/5/2026 |  | $1,530.00 | $0.00 | $1,530.00 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0190 | Exterior Door TK [10001 -20103250 -000] [OP] | 5/5/2026 |  | $4,099.04 | $0.00 | $4,099.04 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0190 | Windows [10001 -20103251 -000] [OP] | 5/5/2026 |  | $5,187.44 | $0.00 | $5,187.44 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0190 | Windows [10001 -20054810 -008] [OH] | 5/5/2026 |  | $355.20 | $0.00 | $355.20 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0007 | Exterior Door TK [10001 -20095932 -000] [OP] | 5/5/2026 |  | $5,168.11 | $0.00 | $5,168.11 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0007 | Windows [10001 -20095933 -000] [OP] | 5/5/2026 |  | $4,611.72 | $0.00 | $4,611.72 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 20 TH | 0001 | Framing Labor-Draw 1 [10001 -20109686 -000] [OP] | 5/5/2026 |  | $8,743.55 | $0.00 | $8,743.55 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Bradshaw Farms Alleys | 0017 | Screens | 5/6/2026 |  | $0.00 | $0.00 | $0.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Signatures | 0083 | Screens | 5/6/2026 |  | $0.00 | $0.00 | $0.00 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0188 | Screens | 5/7/2026 |  | $0.00 | $0.00 | $0.00 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0185 | Screens | 5/7/2026 |  | $0.00 | $0.00 | $0.00 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0040 | Exterior Door TK [10001 -20166579 -000] [OP] | 5/7/2026 |  | $4,069.12 | $0.00 | $4,069.12 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0040 | Windows [10001 -20166580 -000] [OP] | 5/7/2026 |  | $4,503.38 | $0.00 | $4,503.38 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Parsons Valley 40 SFD | 0193 | Frame Punch /Tyvek 2 [10001 -20108916 -000] [OP] | 5/7/2026 |  | $540.00 | $0.00 | $540.00 | Dan Goodrich | (615) 906-5879 | dan.goodrich@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0256 | Exterior Door TK [10001 -20166417 -000] [OP] | 5/7/2026 |  | $3,647.60 | $0.00 | $3,647.60 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0256 | Windows [10001 -20166418 -000] [OP] | 5/7/2026 |  | $3,648.67 | $0.00 | $3,648.67 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0160 | Exterior Door TK [10001 -20167324 -000] [OP] | 5/7/2026 |  | $5,137.04 | $0.00 | $5,137.04 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waterford Park | 0160 | Windows [10001 -20167325 -000] [OP] | 5/7/2026 |  | $5,118.48 | $0.00 | $5,118.48 | Brett zzzMosley | (615) 394-5718 | bmosley@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0026 | Exterior Door TK [10001 -20167701 -000] [OP] | 5/7/2026 |  | $3,351.22 | $0.00 | $3,351.22 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0026 | Windows [10001 -20167702 -000] [OP] | 5/7/2026 |  | $3,494.04 | $0.00 | $3,494.04 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0120 | Exterior Door TK [10001 -20167892 -000] [OP] | 5/7/2026 |  | $3,351.22 | $0.00 | $3,351.22 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0120 | Windows [10001 -20167893 -000] [OP] | 5/7/2026 |  | $3,729.09 | $0.00 | $3,729.09 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0314 | Screens | 5/8/2026 |  | $0.00 | $0.00 | $0.00 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0315 | Screens | 5/8/2026 |  | $0.00 | $0.00 | $0.00 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0316 | Screens | 5/8/2026 |  | $0.00 | $0.00 | $0.00 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0317 | Screens | 5/8/2026 |  | $0.00 | $0.00 | $0.00 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0184 | Screens | 5/8/2026 |  | $0.00 | $0.00 | $0.00 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0021 | Screens | 5/8/2026 |  | $0.00 | $0.00 | $0.00 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0023 | Deliver Frame Package [10001 -20178025 -000] [OP] | 5/8/2026 |  | $24,315.20 | $0.00 | $24,315.20 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0110 | Exterior Door TK [10001 -20166677 -000] [OP] | 5/8/2026 |  | $6,199.21 | $0.00 | $6,199.21 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0110 | Windows [10001 -20166678 -000] [OP] | 5/8/2026 |  | $6,299.91 | $0.00 | $6,299.91 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0023 | Framing Labor-Draw 1 [10001 -20178026 -000] [OP] | 5/11/2026 |  | $10,569.30 | $0.00 | $10,569.30 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0093 | Screens | 5/13/2026 |  | $0.00 | $0.00 | $0.00 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0186 | Exterior Door TK [10001 -20166778 -000] [OP] | 5/13/2026 |  | $4,555.53 | $0.00 | $4,555.53 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Estates 40 | 0186 | Windows [10001 -20166779 -000] [OP] | 5/13/2026 |  | $6,211.06 | $0.00 | $6,211.06 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0318 | Screens | 5/14/2026 |  | $0.00 | $0.00 | $0.00 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Townhome | 0319 | Screens | 5/14/2026 |  | $0.00 | $0.00 | $0.00 | Aneta Stone | (000) 000-1122 | aneta.stone@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Bradshaw Farms Alleys | 0019 | Exterior Door TK [10001 -20155302 -000] [OP] | 5/14/2026 |  | $421.52 | $0.00 | $421.52 | Cynthia Zubia | (615) 887-2898 | cynthia.zubia@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Bradshaw Farms Alleys | 0019 | Windows [10001 -20155303 -000] [OP] | 5/14/2026 |  | $0.00 | $0.00 | $0.00 | Cynthia Zubia | (615) 887-2898 | cynthia.zubia@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0027 | Screens | 5/14/2026 |  | $0.00 | $0.00 | $0.00 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Bradshaw Farms Alleys | 0025 | Exterior Door TK [10001 -20163104 -000] [OP] | 5/14/2026 |  | $421.52 | $0.00 | $421.52 | Cynthia Zubia | (615) 887-2898 | cynthia.zubia@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Bradshaw Farms Alleys | 0025 | Windows [10001 -20163105 -000] [OP] | 5/14/2026 |  | $0.00 | $0.00 | $0.00 | Cynthia Zubia | (615) 887-2898 | cynthia.zubia@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0041 | Exterior Door TK [10001 -20168338 -000] [OP] | 5/14/2026 |  | $4,069.12 | $0.00 | $4,069.12 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0041 | Windows [10001 -20168339 -000] [OP] | 5/14/2026 |  | $4,869.80 | $0.00 | $4,869.80 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0112 | Exterior Door TK [10001 -20168471 -000] [OP] | 5/14/2026 |  | $4,069.12 | $0.00 | $4,069.12 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0112 | Windows [10001 -20168472 -000] [OP] | 5/14/2026 |  | $3,754.68 | $0.00 | $3,754.68 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Signatures | 0084 | Exterior Door TK [10001 -20168680 -000] [OP] | 5/14/2026 |  | $4,387.04 | $0.00 | $4,387.04 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Windtree Signatures | 0084 | Windows [10001 -20168681 -000] [OP] | 5/14/2026 |  | $4,459.32 | $0.00 | $4,459.32 | Jason Fritz | (615) 500-4836 | jason.fritz@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0116 | Exterior Door TK [10001 -20168808 -000] [OP] | 5/14/2026 |  | $3,386.81 | $0.00 | $3,386.81 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 30 Phase 2 | 0116 | Windows [10001 -20168809 -000] [OP] | 5/14/2026 |  | $4,474.61 | $0.00 | $4,474.61 | Joshua Kelzer | (615) 571-5298 | joshua.kelzer@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0038 | Deliver Frame Package [10001 -20190232 -000] [OP] | 5/15/2026 |  | $25,153.56 | $0.00 | $25,153.56 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Waverly 40s | 0269 | Screens | 5/18/2026 |  | $0.00 | $0.00 | $0.00 | Kyle zzzSalisbury | (000) 000-1122 | kyle.salisbury@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0040 | Frame Punch /Tyvek 2 [10001 -20166576 -000] [OP] | 5/19/2026 |  | $540.00 | $0.00 | $540.00 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0023 | Exterior Door TK [10001 -20178030 -000] [OP] | 5/21/2026 |  | $2,929.70 | $0.00 | $2,929.70 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0023 | Windows [10001 -20178031 -000] [OP] | 5/21/2026 |  | $3,228.80 | $0.00 | $3,228.80 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0041 | Frame Punch /Tyvek 2 [10001 -20168335 -000] [OP] | 5/26/2026 |  | $540.00 | $0.00 | $540.00 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Bradshaw Farms Alleys | 0021 | Screens | 5/26/2026 |  | $0.00 | $0.00 | $0.00 | Chris Jeffers | (615) 509-5085 | chris.jeffers@beazer.com | Incomplete
Beazer Homes - 52 Nashville Division - ,1213 | Overlook At Aarons Cress | 0051 | Screens | 6/2/2026 |  | $0.00 | $0.00 | $0.00 | Nathan zzzCarter | (602) 501-0690 | nathan.carter@beazer.com | Incomplete