## SupplyPro Orders
Builder Name | Subdivision | Lot / Block | Task | Requested Start Date | Actual Start Date | Subtotal | Tax | Total | Contact Name | Contact Phone | Contact Email | Status
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1005 | Frame Labor 1 (411205) (INT) [7966414 - 72049751-000] [OP] | 4/16/2026 |  | $44,215.34 | $0.00 | $44,215.34 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0101 / PHASE 2 LOT 101 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 79435583-000] [OP] | 4/17/2026 |  | $2,843.90 | $277.29 | $3,121.19 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0202 / SECTION 2 LOT 202 | Exterior Doors (435401) (EXT) [7966414 - 68075383-000] [OP] | 4/17/2026 |  | $671.00 | $55.67 | $726.67 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0211 / SECTION 2 LOT 211 | Roof Trusses Delivery (411028) (EXT) [7966414 - 71042013-000] [OP] | 4/20/2026 |  | $5,620.10 | $547.96 | $6,168.06 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0101 / PHASE 2 LOT 101 | Roof Trusses Delivery (411028) (EXT) [7966414 - 79435575-000] [OP] | 4/20/2026 |  | $3,200.68 | $312.07 | $3,512.75 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0100 / PHASE 2 LOT 100 | Roof Trusses Delivery (411028) (EXT) [7966414 - 79975601-000] [OP] | 4/20/2026 |  | $2,727.34 | $265.92 | $2,993.26 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0200 / SECTION 2 LOT 200 | Exterior Doors (435401) (EXT) [7966414 - 68040797-000] [OP] | 4/20/2026 |  | $671.01 | $55.67 | $726.68 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0101 / PHASE 2 LOT 101 | Frame Labor 1 (411205) (INT) [7966414 - 79435604-000] [OP] | 4/20/2026 |  | $6,887.94 | $0.00 | $6,887.94 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0100 / PHASE 2 LOT 100 | Frame Labor 1 (411205) (INT) [7966414 - 79975707-000] [OP] | 4/20/2026 |  | $6,350.08 | $0.00 | $6,350.08 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0100 / LOT 100 | SP-EPO: Exterior Doors (435401) (EXT) SILL OVERLAY [7966414 - 85702174-000] [UA] | 4/20/2026 |  | $210.57 | $0.00 | $210.57 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0007 / PHASE 1 LOT 7 | SP-EPO: Window Delivery and Install (423401)FXD GL [7966414 - 85710801-000] [UA] | 4/21/2026 |  | $290.24 | $0.00 | $290.24 | Joseph Benzinger | (615) 418-2085 | joseph.benzinger@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Parkside - 2236751 | 0013 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 47648648-000] [OP] | 4/22/2026 | 2/3/2026 | $12,054.98 | $1,175.36 | $13,230.34 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0111 / PHASE 2 LOT 111 | Exterior Doors (435401) (EXT) [LS] [7966414 - 50289287-000] [OP] | 4/22/2026 |  | $671.01 | $55.67 | $726.68 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0091 / PHASE 1A LOT 91 | Exterior Doors (435401) (EXT) [7966414 - 64062041-000] [OP] | 4/22/2026 |  | $636.65 | $52.32 | $688.97 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0212 / SECTION 2 LOT 212 | Roof Trusses Delivery (411028) (EXT) [7966414 - 75273898-000] [OP] | 4/23/2026 |  | $6,626.76 | $646.10 | $7,272.86 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0208 / SECTION 2 LOT 208 | Window Delivery and Install (423401) (INT) [7966414 - 70139569-000] [OP] | 4/24/2026 |  | $5,764.72 | $439.66 | $6,204.38 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Parkside Estates - 3200861 | 0021 | Window Delivery and Install (423401) (INT) [7966414 - 72113506-000] [OP] | 4/24/2026 |  | $2,990.54 | $233.55 | $3,224.09 | Quinton Miller | (615) 840-1839 | quinton.miller@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Parkside Estates - 3200861 | 0018 | Window Delivery and Install (423401) (INT) [7966414 - 72112343-000] [OP] | 4/24/2026 |  | $2,990.54 | $233.55 | $3,224.09 | Quinton Miller | (615) 840-1839 | quinton.miller@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0011 / PHASE 2 LOT 11 | Window Delivery and Install (423401) (INT) [7966414 - 75267826-000] [OP] | 4/24/2026 |  | $5,460.00 | $425.55 | $5,885.55 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0178 / SECTION 2 LOT 178 | Roof Trusses Delivery (411028) (EXT) [7966414 - 78643313-000] [OP] | 4/24/2026 |  | $3,944.30 | $384.57 | $4,328.87 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0088 | Roof Trusses Delivery (411028) (EXT) [7966414 - 79224567-000] [OP] | 4/24/2026 |  | $5,676.51 | $553.46 | $6,229.97 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0208 / SECTION 2 LOT 208 | Exterior Doors (435401) (EXT) [7966414 - 70139577-000] [OP] | 4/24/2026 |  | $671.00 | $55.67 | $726.67 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0171 / SECTION 2 3 LOT 171 | Window Screen Install (INT) | 4/24/2026 |  | $0.00 | $0.00 | $0.00 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Parkside Estates - 3200861 | 0018 | Exterior Doors (435401) (EXT) [7966414 - 72112351-000] [OP] | 4/24/2026 |  | $636.65 | $52.32 | $688.97 | Quinton Miller | (615) 840-1839 | quinton.miller@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Parkside Estates - 3200861 | 0021 | Exterior Doors (435401) (EXT) [7966414 - 72113514-000] [OP] | 4/24/2026 |  | $636.65 | $52.32 | $688.97 | Quinton Miller | (615) 840-1839 | quinton.miller@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0011 / PHASE 2 LOT 11 | Exterior Doors (435401) (EXT) [7966414 - 75267834-000] [OP] | 4/24/2026 |  | $671.01 | $55.67 | $726.68 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0075 / PHASE 1 LOT 75 | Exterior Doors (435401) (EXT) [LS] [7966414 - 33238541-000] [OP] | 4/24/2026 |  | $778.99 | $66.20 | $845.19 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1007 | Frame Labor 1 (411205) (INT) [7966414 - 80527418-000] [OP] | 4/24/2026 |  | $44,215.34 | $0.00 | $44,215.34 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0019 / PHASE 2 LOT 19 | stolen titan bolts [7966414 - 87399658-000] [UA] | 4/24/2026 |  | $159.14 | $0.00 | $159.14 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0101 / PHASE 2 LOT 101 | EPO: I-Joist Material 2nd Floor (411031) (INT) [7966414 - 87620252-000] [UA] | 4/24/2026 |  | $257.66 | $0.00 | $257.66 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0428 / PHASE 2 A LOT 428 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 33438738-000] [OP] | 4/27/2026 |  | $2,123.71 | $166.59 | $2,290.30 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0200 / SECTION 2 LOT 200 | Window Delivery and Install (423401) (INT) [7966414 - 68040789-000] [OP] | 4/27/2026 |  | $3,684.64 | $293.91 | $3,978.55 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Ridge - 2239651 | 0158 / SECTION 2 LOT 158 | Window Delivery and Install (423401) (INT) [7966414 - 69342586-000] [OP] | 4/27/2026 |  | $5,655.75 | $440.27 | $6,096.02 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0369 / SECTION 2A LOT 369 | Window Delivery and Install (423401) (INT) [7966414 - 69769192-000] [OP] | 4/27/2026 |  | $3,958.60 | $309.89 | $4,268.49 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Ridge - 2239651 | 0161 / SECTION 2 LOT 161 | Window Delivery and Install (423401) (INT) [7966414 - 72108344-000] [OP] | 4/27/2026 |  | $5,655.75 | $440.27 | $6,096.02 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0370 / SECTION 2A LOT 370 | Window Delivery and Install (423401) (INT) [7966414 - 72670492-000] [OP] | 4/27/2026 |  | $3,800.54 | $296.92 | $4,097.46 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0012 / PHASE 2 LOT 12 | Window Delivery and Install (423401) (INT) [7966414 - 75100049-000] [OP] | 4/27/2026 |  | $5,443.22 | $432.21 | $5,875.43 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Ridge - 2239651 | 0161 / SECTION 2 LOT 161 | Exterior Doors (435401) (EXT) [7966414 - 72108352-000] [OP] | 4/27/2026 |  | $1,164.06 | $103.74 | $1,267.80 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0066 | Roof Trusses Delivery (411028) (EXT) [7966414 - 77911136-000] [OP] | 4/27/2026 |  | $6,394.24 | $623.43 | $7,017.67 | Corey Burke | (615) 753-9159 | corey.burke@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0369 / SECTION 2A LOT 369 | Exterior Doors (435401) (EXT) [7966414 - 69769205-000] [OP] | 4/27/2026 |  | $671.00 | $55.67 | $726.67 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0370 / SECTION 2A LOT 370 | Exterior Doors (435401) (EXT) [7966414 - 72670505-000] [OP] | 4/27/2026 |  | $1,366.60 | $113.74 | $1,480.34 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0087 | Roof Trusses Delivery (411028) (EXT) [7966414 - 79223249-000] [OP] | 4/27/2026 |  | $4,915.52 | $479.26 | $5,394.78 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0428 / PHASE 2 A LOT 428 | Exterior Doors (435401) (EXT) [LS] [7966414 - 33438746-000] [OP] | 4/27/2026 |  | $732.61 | $61.68 | $794.29 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Ridge - 2239651 | 0158 / SECTION 2 LOT 158 | Exterior Doors (435401) (EXT) [7966414 - 69342623-000] [OP] | 4/27/2026 |  | $1,164.06 | $103.74 | $1,267.80 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0165 / SECTION 2 3 LOT 165 | Exterior Doors (435401) (EXT) [7966414 - 79972645-000] [OP] | 4/27/2026 |  | $671.00 | $55.67 | $726.67 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0012 / PHASE 2 LOT 12 | Exterior Doors (435401) (EXT) [7966414 - 75100057-000] [OP] | 4/27/2026 |  | $671.01 | $55.67 | $726.68 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - One Lebanon Row - 2239551 | 1002 | Window Delivery and Install (423401) (INT) [7966414 - 87141577-000] [OP] | 4/27/2026 |  | $16,454.89 | $1,321.05 | $17,775.94 | John Wetherington | (615) 630-1858 | john.wetherington@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - One Lebanon Row - 2239551 | 1002 | Exterior Doors (435401) (EXT) [7966414 - 87141585-000] [OP] | 4/27/2026 |  | $8,475.98 | $680.15 | $9,156.13 | John Wetherington | (615) 630-1858 | john.wetherington@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - One Lebanon - Avenue - 2239451 | 3008 | Deck Material (411055) (EXT) [7966414 - 59992024-000] [OP] | 4/27/2026 |  | $1,611.84 | $157.17 | $1,769.01 | John Wetherington | (615) 630-1858 | john.wetherington@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Lisenbee Fields - 3202451 | 0127 / PHASE 1B LOT 127 | Window Screen Install (INT) | 4/27/2026 |  | $0.00 | $0.00 | $0.00 | Gregg Tinnell | (629) 252-8336 | Gregg.Tinnell@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Lisenbee Fields - 3202451 | 0126 / PHASE 1B LOT 126 | Window Screen Install (INT) | 4/27/2026 |  | $0.00 | $0.00 | $0.00 | Gregg Tinnell | (629) 252-8336 | Gregg.Tinnell@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0091 / PHASE 1A LOT 91 | Window Delivery and Install (423401) (INT) [7966414 - 64062032-000] [OP] | 4/28/2026 |  | $3,150.11 | $244.72 | $3,394.83 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0178 / SECTION 2 3 LOT 178 | Prefab Stairs (411801) (INT) [7966414 - 76707627-000] [OP] | 4/28/2026 |  | $740.18 | $72.17 | $812.35 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0163 / SECTION 2 3 LOT 163 | Window Delivery and Install (423401) (INT) [7966414 - 79220603-000] [OP] | 4/28/2026 |  | $5,764.72 | $439.66 | $6,204.38 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0163 / SECTION 2 3 LOT 163 | Exterior Doors (435401) (EXT) [7966414 - 79220611-000] [OP] | 4/28/2026 |  | $1,241.99 | $111.34 | $1,353.33 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0170 / SECTION 2 3 LOT 170 | Window Screen Install (INT) | 4/28/2026 |  | $0.00 | $0.00 | $0.00 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0163 / PHASE 1B LOT 163 | Window Screen Install (INT) | 4/28/2026 |  | $0.00 | $0.00 | $0.00 | Ron Huckaby | (615) 630-5414 | Ron.Huckaby@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0164 / PHASE 1B LOT 164 | Window Screen Install (INT) | 4/28/2026 |  | $0.00 | $0.00 | $0.00 | Ron Huckaby | (615) 630-5414 | Ron.Huckaby@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0367 / SECTION 2A LOT 367 | Window Delivery and Install (423401) (INT) [7966414 - 72168620-000] [OP] | 4/29/2026 |  | $4,200.29 | $334.92 | $4,535.21 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0019 / PHASE 2 LOT 19 | Window Delivery and Install (423401) (INT) [7966414 - 75101375-000] [OP] | 4/29/2026 |  | $5,301.31 | $418.39 | $5,719.70 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0113 / PHASE 2 LOT 113 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 75269055-000] [OP] | 4/29/2026 |  | $2,843.90 | $277.29 | $3,121.19 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0093 / PHASE 1A LOT 93 | Window Delivery and Install (423401) (INT) [7966414 - 75104592-000] [OP] | 4/29/2026 |  | $2,990.54 | $233.55 | $3,224.09 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0212 / SECTION 2 LOT 212 | Prefab Stairs (411801) (INT) [7966414 - 75273901-000] [OP] | 4/29/2026 |  | $740.18 | $72.17 | $812.35 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Ridge - 2239651 | 0163 / SECTION 2 LOT 163 | Prefab Stairs (411801) (INT) [7966414 - 72110997-000] [OP] | 4/29/2026 |  | $740.18 | $72.17 | $812.35 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0101 / PHASE 2 LOT 101 | Window Delivery and Install (423401) (INT) [7966414 - 79435621-000] [OP] | 4/29/2026 |  | $3,305.82 | $255.52 | $3,561.34 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0100 / PHASE 2 LOT 100 | Window Delivery and Install (423401) (INT) [7966414 - 79975731-000] [OP] | 4/29/2026 |  | $3,374.17 | $264.13 | $3,638.30 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0367 / SECTION 2A LOT 367 | Exterior Doors (435401) (EXT) [7966414 - 72168638-000] [OP] | 4/29/2026 |  | $671.00 | $55.67 | $726.67 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0019 / PHASE 2 LOT 19 | Exterior Doors (435401) (EXT) [7966414 - 75101391-000] [OP] | 4/29/2026 |  | $671.01 | $55.67 | $726.68 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0101 / PHASE 2 LOT 101 | Exterior Doors (435401) (EXT) [7966414 - 79435639-000] [OP] | 4/29/2026 |  | $671.01 | $55.67 | $726.68 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0100 / PHASE 2 LOT 100 | Exterior Doors (435401) (EXT) [7966414 - 79975740-000] [OP] | 4/29/2026 |  | $671.01 | $55.67 | $726.68 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0093 / PHASE 1A LOT 93 | Exterior Doors (435401) (EXT) [7966414 - 75104613-000] [OP] | 4/29/2026 |  | $636.65 | $52.32 | $688.97 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0075 / PHASE 1 LOT 75 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 33238533-000] [OP] | 4/30/2026 |  | $4,214.85 | $321.71 | $4,536.56 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0027 / PHASE 1 LOT 27 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 52897526-000] [OP] | 4/30/2026 |  | $2,587.06 | $208.84 | $2,795.90 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0430 / PHASE 2 A LOT 430 | Window Delivery and Install (423401) (INT) [7966414 - 67472512-000] [OP] | 4/30/2026 |  | $2,161.02 | $170.23 | $2,331.25 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0575 / SECTION 2A LOT 575 | Window Delivery and Install (423401) (INT) [7966414 - 72171010-000] [OP] | 4/30/2026 |  | $4,214.85 | $321.71 | $4,536.56 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0574 / SECTION 2A LOT 574 | Window Delivery and Install (423401) (INT) [7966414 - 72107131-000] [OP] | 4/30/2026 |  | $3,987.05 | $308.78 | $4,295.83 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0203 / SECTION 2 LOT 203 | Roof Trusses Delivery (411028) (EXT) [7966414 - 75102837-000] [OP] | 4/30/2026 |  | $5,556.56 | $541.76 | $6,098.32 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0113 / PHASE 2 LOT 113 | Roof Trusses Delivery (411028) (EXT) [7966414 - 75269047-000] [OP] | 4/30/2026 |  | $3,268.30 | $318.66 | $3,586.96 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0372 / SECTION 2A LOT 372 | Window Delivery and Install (423401) (INT) [7966414 - 46830667-000] [OP] | 4/30/2026 |  | $3,528.60 | $268.94 | $3,797.54 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0201 / SECTION 2 LOT 201 | Roof Trusses Delivery (411028) (EXT) [7966414 - 79221833-000] [OP] | 4/30/2026 |  | $5,770.24 | $562.60 | $6,332.84 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0574 / SECTION 2A LOT 574 | Exterior Doors (435401) (EXT) [7966414 - 72107149-000] [OP] | 4/30/2026 |  | $1,366.60 | $113.74 | $1,480.34 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0575 / SECTION 2A LOT 575 | Exterior Doors (435401) (EXT) [7966414 - 72171028-000] [OP] | 4/30/2026 |  | $671.00 | $55.67 | $726.67 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0027 / PHASE 1 LOT 27 | Exterior Doors (435401) (EXT) [LS] [7966414 - 52897534-000] [OP] | 4/30/2026 |  | $779.01 | $66.20 | $845.21 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0368 / SECTION 2A LOT 368 | Exterior Doors (435401) (EXT) [7966414 - 72169825-000] [OP] | 4/30/2026 |  | $1,304.98 | $107.73 | $1,412.71 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0430 / PHASE 2 A LOT 430 | Exterior Doors (435401) (EXT) [7966414 - 67472521-000] [OP] | 4/30/2026 |  | $1,365.21 | $123.36 | $1,488.57 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0579 / SECTION 2A LOT 579 | Window Screen Install (INT) | 4/30/2026 |  | $0.00 | $0.00 | $0.00 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0009 / SECTION 1 PHASE 2 LOT 9 | Window Screen Install (INT) [LS] | 4/30/2026 |  | $0.00 | $0.00 | $0.00 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0162 / PHASE 1B LOT 162 | Roof Trusses Delivery (411028) (EXT) [7966414 - 72234906-000] [OP] | 5/1/2026 |  | $5,766.67 | $562.25 | $6,328.92 | Corey Burke | (615) 753-9159 | corey.burke@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0368 / SECTION 2A LOT 368 | Window Delivery and Install (423401) (INT) [7966414 - 72169817-000] [OP] | 5/1/2026 |  | $3,448.41 | $263.06 | $3,711.47 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0203 / SECTION 2 LOT 203 | Prefab Stairs (411801) (INT) [7966414 - 75102845-000] [OP] | 5/1/2026 |  | $740.18 | $72.17 | $812.35 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0092 / PHASE 1A LOT 92 | Window Delivery and Install (423401) (INT) [7966414 - 76510437-000] [OP] | 5/1/2026 |  | $2,944.64 | $229.07 | $3,173.71 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0130 | Window Delivery and Install (423401) (INT) [7966414 - 76846598-000] [OP] | 5/1/2026 |  | $4,880.77 | $383.71 | $5,264.48 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0114 | Window Delivery and Install (423401) (INT) [7966414 - 76845317-000] [OP] | 5/1/2026 |  | $4,880.77 | $383.71 | $5,264.48 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0114 | Exterior Doors (435401) (EXT) [7966414 - 76845325-000] [OP] | 5/1/2026 |  | $1,164.06 | $103.74 | $1,267.80 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0130 | Exterior Doors (435401) (EXT) [7966414 - 76846601-000] [OP] | 5/1/2026 |  | $1,164.06 | $103.74 | $1,267.80 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0201 / SECTION 2 LOT 201 | Prefab Stairs (411801) (INT) [7966414 - 79221841-000] [OP] | 5/1/2026 |  | $740.18 | $72.17 | $812.35 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0161 / PHASE 1B LOT 161 | Roof Trusses Delivery (411028) (EXT) [7966414 - 72377747-000] [OP] | 5/1/2026 |  | $5,319.44 | $518.65 | $5,838.09 | Corey Burke | (615) 753-9159 | corey.burke@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0092 / PHASE 1A LOT 92 | Exterior Doors (435401) (EXT) [7966414 - 76510445-000] [OP] | 5/1/2026 |  | $636.65 | $52.32 | $688.97 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0047 / SECTION 1 LOT 47 | Roof Trusses Delivery (411028) (EXT) [7966414 - 81199858-000] [OP] | 5/1/2026 |  | $10,909.36 | $1,063.66 | $11,973.02 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0211 / SECTION 2 LOT 211 | Prefab Stairs (411801) (INT) [7966414 - 71042021-000] [OP] | 5/4/2026 |  | $740.18 | $72.17 | $812.35 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0212 / SECTION 2 LOT 212 | Window Delivery and Install (423401) (INT) [7966414 - 75273919-000] [OP] | 5/4/2026 |  | $5,344.10 | $422.54 | $5,766.64 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0066 | Window Delivery and Install (423401) (INT) [7966414 - 77911144-000] [OP] | 5/4/2026 |  | $4,159.57 | $320.71 | $4,480.28 | Corey Burke | (615) 753-9159 | corey.burke@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0178 / SECTION 2 LOT 178 | Prefab Stairs (411801) (INT) [7966414 - 78643321-000] [OP] | 5/4/2026 |  | $740.18 | $72.17 | $812.35 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0088 | Window Delivery and Install (423401) (INT) [7966414 - 79224575-000] [OP] | 5/4/2026 |  | $4,200.29 | $334.92 | $4,535.21 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0087 | Window Delivery and Install (423401) (INT) [7966414 - 79223257-000] [OP] | 5/4/2026 |  | $3,784.60 | $289.03 | $4,073.63 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1008 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 80528120-000] [OP] | 5/4/2026 |  | $20,200.23 | $1,969.53 | $22,169.76 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0066 | Exterior Doors (435401) (EXT) [7966414 - 77911152-000] [OP] | 5/4/2026 |  | $671.00 | $55.67 | $726.67 | Corey Burke | (615) 753-9159 | corey.burke@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0087 | Exterior Doors (435401) (EXT) [7966414 - 79223265-000] [OP] | 5/4/2026 |  | $1,366.60 | $113.74 | $1,480.34 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0088 | Exterior Doors (435401) (EXT) [7966414 - 79224583-000] [OP] | 5/4/2026 |  | $671.00 | $55.67 | $726.67 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0212 / SECTION 2 LOT 212 | Exterior Doors (435401) (EXT) [7966414 - 75273927-000] [OP] | 5/4/2026 |  | $671.01 | $55.67 | $726.68 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1005 | Window Delivery and Install (423401) (INT) [7966414 - 72049778-000] [OP] | 5/5/2026 |  | $16,489.27 | $1,310.27 | $17,799.54 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1005 | Exterior Doors (435401) (EXT) [7966414 - 72049786-000] [OP] | 5/5/2026 |  | $4,465.03 | $376.84 | $4,841.87 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Lisenbee Fields - 3202451 | 0123 / PHASE 1B LOT 123 | Window Delivery and Install (423401) (INT) [7966414 - 75276280-000] [OP] | 5/5/2026 |  | $3,305.82 | $255.52 | $3,561.34 | Gregg Tinnell | (629) 252-8336 | Gregg.Tinnell@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Lisenbee Fields - 3202451 | 0124 / PHASE 1B LOT 124 | Window Delivery and Install (423401) (INT) [7966414 - 75277469-000] [OP] | 5/5/2026 |  | $3,709.32 | $288.02 | $3,997.34 | Gregg Tinnell | (629) 252-8336 | Gregg.Tinnell@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0149 | Prefab Stairs (411801) (INT) [7966414 - 79434290-000] [OP] | 5/5/2026 |  | $740.18 | $72.17 | $812.35 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1007 | Roof Trusses Delivery (411028) (EXT) [7966414 - 80527389-000] [OP] | 5/5/2026 |  | $21,730.50 | $2,118.72 | $23,849.22 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0157 | Prefab Stairs (411801) (INT) [7966414 - 84365621-000] [OP] | 5/5/2026 |  | $740.18 | $72.17 | $812.35 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0113 / PHASE 2 LOT 113 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [7966414 - 75269063-000] [OP] | 5/5/2026 |  | $898.78 | $87.62 | $986.40 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0113 / PHASE 2 LOT 113 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [7966414 - 75269039-000] [OP] | 5/5/2026 |  | $7,304.03 | $712.11 | $8,016.14 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0114 / PHASE 2 LOT 114 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 84366922-000] [OP] | 5/5/2026 |  | $3,806.13 | $371.10 | $4,177.23 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0114 / PHASE 2 LOT 114 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [7966414 - 84366931-000] [OP] | 5/5/2026 |  | $836.53 | $81.56 | $918.09 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0114 / PHASE 2 LOT 114 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [7966414 - 84366906-000] [OP] | 5/5/2026 |  | $8,217.25 | $801.16 | $9,018.41 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0028 / PHASE 1 LOT 28 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 16548610-000] [OP] | 5/6/2026 |  | $2,587.06 | $208.84 | $2,795.90 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0007 / PHASE 2 LOT 7 | Window Delivery and Install (423401) (INT) [7966414 - 75265281-000] [OP] | 5/6/2026 |  | $4,797.84 | $369.78 | $5,167.62 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Ridge - 2239651 | 0163 / SECTION 2 LOT 163 | Window Delivery and Install (423401) (INT) [7966414 - 72111009-000] [OP] | 5/6/2026 |  | $5,655.75 | $440.27 | $6,096.02 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0094 / PHASE 1A LOT 94 | Window Delivery and Install (423401) (INT) [7966414 - 75105974-000] [OP] | 5/6/2026 |  | $2,987.02 | $233.21 | $3,220.23 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0094 / PHASE 1A LOT 94 | Exterior Doors (435401) (EXT) [7966414 - 75106002-000] [OP] | 5/6/2026 |  | $636.65 | $52.32 | $688.97 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Ridge - 2239651 | 0163 / SECTION 2 LOT 163 | Exterior Doors (435401) (EXT) [7966414 - 72111017-000] [OP] | 5/6/2026 |  | $1,164.06 | $103.74 | $1,267.80 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0114 / PHASE 2 LOT 114 | Roof Trusses Delivery (411028) (EXT) [7966414 - 84366914-000] [OP] | 5/6/2026 |  | $3,746.15 | $365.25 | $4,111.40 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Parkside - 2236751 | 0013 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 47648816-000] [OP] | 5/7/2026 | 2/19/2026 | $11,681.56 | $930.26 | $12,611.82 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Parkside - 2236751 | 0013 | Exterior Doors (435401) (EXT) [LS] [7966414 - 47648883-000] [OP] | 5/7/2026 |  | $3,408.69 | $293.35 | $3,702.04 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0431 / PHASE 2 A LOT 431 | Window Delivery and Install (423401) (INT) [7966414 - 64095580-000] [OP] | 5/7/2026 |  | $1,921.75 | $151.28 | $2,073.03 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Ridge - 2239651 | 0162 / SECTION 2 LOT 162 | Window Delivery and Install (423401) (INT) [7966414 - 72109603-000] [OP] | 5/7/2026 |  | $5,074.02 | $394.76 | $5,468.78 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0209 / SECTION 2 LOT 209 | Roof Trusses Delivery (411028) (EXT) [7966414 - 75272529-000] [OP] | 5/7/2026 |  | $5,085.02 | $495.79 | $5,580.81 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0162 / SECTION 2 3 LOT 162 | Prefab Stairs (411801) (INT) [7966414 - 76705040-000] [OP] | 5/7/2026 |  | $740.18 | $72.17 | $812.35 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0128 / SECTION 2 3 LOT 128 | Prefab Stairs (411801) (INT) [7966414 - 76717497-000] [OP] | 5/7/2026 |  | $740.18 | $72.17 | $812.35 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1008 | Roof Trusses Delivery (411028) (EXT) [7966414 - 80528111-000] [OP] | 5/7/2026 |  | $21,730.50 | $2,118.72 | $23,849.22 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0106 | Roof Trusses Delivery (411028) (EXT) [7966414 - 81983183-000] [OP] | 5/7/2026 |  | $3,756.07 | $366.22 | $4,122.29 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0089 | Roof Trusses Delivery (411028) (EXT) [7966414 - 81894455-000] [OP] | 5/7/2026 |  | $5,963.75 | $581.46 | $6,545.21 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0431 / PHASE 2 A LOT 431 | Exterior Doors (435401) (EXT) [7966414 - 64095598-000] [OP] | 5/7/2026 |  | $732.61 | $61.68 | $794.29 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0003 | Window Screen Install (INT) | 5/7/2026 |  | $0.00 | $0.00 | $0.00 | Ron Huckaby | (615) 630-5414 | Ron.Huckaby@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0077 / PHASE 1 LOT 77 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 53115725-000] [OP] | 5/7/2026 |  | $3,756.07 | $366.22 | $4,122.29 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0211 / SECTION 2 LOT 211 | Window Delivery and Install (423401) (INT) [7966414 - 71042030-000] [OP] | 5/8/2026 |  | $5,525.01 | $427.50 | $5,952.51 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0178 / SECTION 2 3 LOT 178 | Window Delivery and Install (423401) (INT) [7966414 - 76707635-000] [OP] | 5/8/2026 |  | $5,525.01 | $427.50 | $5,952.51 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0209 / SECTION 2 LOT 209 | Prefab Stairs (411801) (INT) [7966414 - 75272537-000] [OP] | 5/8/2026 |  | $740.18 | $72.17 | $812.35 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0178 / SECTION 2 3 LOT 178 | Exterior Doors (435401) (EXT) [7966414 - 76707643-000] [OP] | 5/8/2026 |  | $670.99 | $55.67 | $726.66 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0211 / SECTION 2 LOT 211 | Exterior Doors (435401) (EXT) [7966414 - 71042048-000] [OP] | 5/8/2026 |  | $671.00 | $55.67 | $726.67 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0102 / PHASE 2 LOT 102 | Window Screen Install (INT) [LS] | 5/8/2026 |  | $0.00 | $0.00 | $0.00 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0011 / LOT 11 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [7966414 - 75511497-000] [OP] | 5/8/2026 |  | $5,367.35 | $523.32 | $5,890.67 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0011 / LOT 11 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [7966414 - 75511542-000] [OP] | 5/8/2026 |  | $1,096.24 | $106.89 | $1,203.13 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0432 / PHASE 2 A LOT 432 | Window Delivery and Install (423401) (INT) [7966414 - 64096777-000] [OP] | 5/11/2026 |  | $2,319.13 | $181.26 | $2,500.39 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0416 / PHASE 2A LOT 416 | Window Delivery and Install (423401) (INT) [7966414 - 75275156-000] [OP] | 5/11/2026 |  | $2,990.54 | $233.55 | $3,224.09 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0167 / SECTION 2 3 LOT 167 | Prefab Stairs (411801) (INT) [7966414 - 76706325-000] [OP] | 5/11/2026 |  | $740.18 | $72.17 | $812.35 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0417 / PHASE 2A LOT | Window Delivery and Install (423401) (INT) [7966414 - 82859731-000] [OP] | 5/11/2026 |  | $2,944.64 | $229.07 | $3,173.71 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Cottage - 2236851 | 0015 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 85399961-000] [OP] | 5/11/2026 |  | $10,613.18 | $1,034.78 | $11,647.96 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0047 / SECTION 1 LOT 47 | Window Delivery and Install (423401) (INT) [7966414 - 33926744-000] [OP] | 5/12/2026 |  | $5,120.16 | $412.45 | $5,532.61 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0433 / PHASE 2 A LOT 433 | Window Delivery and Install (423401) (INT) [7966414 - 67473697-000] [OP] | 5/12/2026 |  | $2,161.02 | $170.23 | $2,331.25 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0162 / PHASE 1B LOT 162 | Window Delivery and Install (423401) (INT) [7966414 - 72234914-000] [OP] | 5/12/2026 |  | $3,812.72 | $303.96 | $4,116.68 | Corey Burke | (615) 753-9159 | corey.burke@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0047 / SECTION 1 LOT 47 | Exterior Doors (435401) (EXT) [7966414 - 33926789-000] [OP] | 5/12/2026 |  | $1,164.04 | $103.74 | $1,267.78 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0178 / SECTION 2 LOT 178 | Window Delivery and Install (423401) (INT) [7966414 - 78643330-000] [OP] | 5/12/2026 |  | $3,958.60 | $309.89 | $4,268.49 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0077 / PHASE 1 LOT 77 | Exterior Doors (435401) (EXT) [LS] [7966414 - 53115741-000] [OP] | 5/12/2026 |  | $671.01 | $55.67 | $726.68 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0078 / PHASE 1 LOT 78 | Exterior Doors (435401) (EXT) [LS] [7966414 - 44131951-000] [OP] | 5/12/2026 |  | $1,474.60 | $124.27 | $1,598.87 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0522 / PHASE 2 A LOT 522 | Window Delivery and Install (423401) (INT) [7966414 - 67474892-000] [OP] | 5/13/2026 |  | $2,161.02 | $170.23 | $2,331.25 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0522 / PHASE 2 A LOT 522 | Exterior Doors (435401) (EXT) [7966414 - 67474905-000] [OP] | 5/13/2026 |  | $1,365.21 | $123.36 | $1,488.57 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0365 / SECTION 2A LOT 365 | Window Delivery and Install (423401) (INT) [7966414 - 75270161-000] [OP] | 5/13/2026 |  | $3,777.60 | $294.68 | $4,072.28 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1007 | Window Delivery and Install (423401) (INT) [7966414 - 80527434-000] [OP] | 5/13/2026 |  | $16,489.27 | $1,310.27 | $17,799.54 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1007 | Exterior Doors (435401) (EXT) [7966414 - 80527442-000] [OP] | 5/13/2026 |  | $4,465.03 | $376.84 | $4,841.87 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0106 | Window Delivery and Install (423401) (INT) [7966414 - 81983191-000] [OP] | 5/13/2026 |  | $4,124.82 | $315.38 | $4,440.20 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0089 | Window Delivery and Install (423401) (INT) [7966414 - 81894463-000] [OP] | 5/13/2026 |  | $4,124.82 | $315.38 | $4,440.20 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0010 / SECTION 1 PHASE 2 LOT 10 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 22712252-000] [OP] | 5/14/2026 | 2/2/2026 | $2,843.90 | $277.29 | $3,121.19 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0576 / SECTION 2A LOT 576 | Window Delivery and Install (423401) (INT) [7966414 - 68071163-000] [OP] | 5/14/2026 |  | $3,528.60 | $268.94 | $3,797.54 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0576 / SECTION 2A LOT 576 | Exterior Doors (435401) (EXT) [7966414 - 68071180-000] [OP] | 5/14/2026 |  | $1,304.98 | $107.73 | $1,412.71 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0203 / SECTION 2 LOT 203 | Window Delivery and Install (423401) (INT) [7966414 - 75102853-000] [OP] | 5/14/2026 |  | $5,473.95 | $426.91 | $5,900.86 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Parkside Estates - 3200861 | 0020 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 78520840-000] [OP] | 5/14/2026 |  | $2,483.94 | $242.18 | $2,726.12 | Quinton Miller | (615) 840-1839 | quinton.miller@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0201 / SECTION 2 LOT 201 | Window Delivery and Install (423401) (INT) [7966414 - 79221850-000] [OP] | 5/14/2026 |  | $5,528.70 | $421.05 | $5,949.75 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Cottage - 2236851 | 0015 | Roof Trusses Delivery (411028) (EXT) [7966414 - 85399953-000] [OP] | 5/14/2026 |  | $10,279.39 | $1,002.24 | $11,281.63 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0010 / SECTION 1 PHASE 2 LOT 10 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 22712236-000] [OP] | 5/14/2026 |  | $7,321.95 | $713.87 | $8,035.82 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0010 / SECTION 1 PHASE 2 LOT 10 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 22712261-000] [OP] | 5/14/2026 |  | $898.78 | $87.62 | $986.40 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0008 / PHASE 2 LOT 8 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 75266541-000] [OP] | 5/15/2026 |  | $4,521.90 | $440.89 | $4,962.79 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0113 / PHASE 2 LOT 113 | Window Delivery and Install (423401) (INT) [7966414 - 75269098-000] [OP] | 5/15/2026 |  | $3,496.69 | $271.68 | $3,768.37 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0149 | Window Delivery and Install (423401) (INT) [7966414 - 79434302-000] [OP] | 5/15/2026 |  | $4,880.77 | $383.71 | $5,264.48 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0160 / PHASE 1B LOT 160 | Roof Trusses Delivery (411028) (EXT) [7966414 - 78516066-000] [OP] | 5/15/2026 |  | $4,991.06 | $486.63 | $5,477.69 | Ron Huckaby | (615) 630-5414 | Ron.Huckaby@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0149 | Exterior Doors (435401) (EXT) [7966414 - 79434311-000] [OP] | 5/15/2026 |  | $1,164.06 | $103.74 | $1,267.80 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0010 / PHASE 2 LOT 10 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 81978237-000] [OP] | 5/15/2026 |  | $3,216.18 | $313.58 | $3,529.76 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0538 / PHASE 2A LOT 538 | Window Delivery and Install (423401) (INT) [7966414 - 82860863-000] [OP] | 5/15/2026 |  | $3,150.11 | $244.72 | $3,394.83 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0114 / PHASE 2 LOT 114 | Window Delivery and Install (423401) (INT) [7966414 - 84366965-000] [OP] | 5/15/2026 |  | $3,541.77 | $274.13 | $3,815.90 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0157 | Window Delivery and Install (423401) (INT) [7966414 - 84365639-000] [OP] | 5/15/2026 |  | $4,880.77 | $383.71 | $5,264.48 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0157 | Exterior Doors (435401) (EXT) [7966414 - 84365647-000] [OP] | 5/15/2026 |  | $1,164.06 | $103.74 | $1,267.80 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0008 / PHASE 2 LOT 8 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [7966414 - 75266532-000] [OP] | 5/15/2026 |  | $8,938.24 | $871.48 | $9,809.72 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0008 / PHASE 2 LOT 8 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [7966414 - 75266559-000] [OP] | 5/15/2026 |  | $1,584.90 | $154.54 | $1,739.44 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0010 / PHASE 2 LOT 10 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [7966414 - 81978245-000] [OP] | 5/15/2026 |  | $1,571.38 | $153.22 | $1,724.60 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0010 / PHASE 2 LOT 10 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [7966414 - 81978211-000] [OP] | 5/15/2026 |  | $8,457.88 | $824.64 | $9,282.52 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0010 / SECTION 1 PHASE 2 LOT 10 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 22712244-000] [OP] | 5/18/2026 | 2/2/2026 | $3,335.00 | $325.16 | $3,660.16 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0008 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 46835943-000] [OP] | 5/18/2026 | 1/20/2026 | $4,639.22 | $452.31 | $5,091.53 | Ken Clark | (661) 281-7143 | ken.clark@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0068 / SECTION 1 LOT 68 | Prefab Stairs (411801) (INT) [7966414 - 75670383-000] [OP] | 5/18/2026 |  | $740.18 | $72.17 | $812.35 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0069 / SECTION 1 LOT 69 | Prefab Stairs (411801) (INT) [7966414 - 75671651-000] [OP] | 5/18/2026 |  | $740.18 | $72.17 | $812.35 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Parkside - 2236751 | 0016 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 85394714-000] [OP] | 5/18/2026 |  | $13,283.68 | $1,295.16 | $14,578.84 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Cottage - 2236851 | 0014 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 85399081-000] [OP] | 5/18/2026 |  | $10,613.18 | $1,034.78 | $11,647.96 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0008 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 46835919-000] [OP] | 5/18/2026 |  | $9,485.06 | $924.82 | $10,409.88 | Ken Clark | (661) 281-7143 | ken.clark@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0008 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 46835978-000] [OP] | 5/18/2026 |  | $1,678.82 | $163.70 | $1,842.52 | Ken Clark | (661) 281-7143 | ken.clark@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0034 / PHASE 1 LOT 34 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 33379635-000] [OP] | 5/19/2026 | 1/23/2026 | $4,350.22 | $424.15 | $4,774.37 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0128 / SECTION 2 3 LOT 128 | Window Delivery and Install (423401) (INT) [7966414 - 76717500-000] [OP] | 5/19/2026 |  | $5,271.96 | $415.53 | $5,687.49 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0162 / SECTION 2 3 LOT 162 | Window Delivery and Install (423401) (INT) [7966414 - 76705058-000] [OP] | 5/19/2026 |  | $5,754.44 | $445.48 | $6,199.92 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0419 / PHASE 2A LOT | Window Delivery and Install (423401) (INT) [7966414 - 79146044-000] [OP] | 5/19/2026 |  | $2,551.17 | $203.87 | $2,755.04 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0420 / PHASE 2A LOT | Window Delivery and Install (423401) (INT) [7966414 - 79147371-000] [OP] | 5/19/2026 |  | $2,990.54 | $233.55 | $3,224.09 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Lisenbee Fields - 3202451 | 0121 / PHASE 1B LOT 121 | Window Delivery and Install (423401) (INT) [7966414 - 79436711-000] [OP] | 5/19/2026 |  | $3,366.20 | $261.40 | $3,627.60 | Gregg Tinnell | (629) 252-8336 | Gregg.Tinnell@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Lisenbee Fields - 3202451 | 0122 / PHASE 1B LOT 122 | Window Delivery and Install (423401) (INT) [7966414 - 79437870-000] [OP] | 5/19/2026 |  | $3,531.96 | $275.12 | $3,807.08 | Gregg Tinnell | (629) 252-8336 | Gregg.Tinnell@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0162 / SECTION 2 3 LOT 162 | Exterior Doors (435401) (EXT) [7966414 - 76705066-000] [OP] | 5/19/2026 |  | $670.99 | $55.67 | $726.66 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0037 / PHASE 1 LOT 37 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 81980708-000] [OP] | 5/19/2026 |  | $4,639.22 | $452.31 | $5,091.53 | Mackenzie Lennon | (615) 856-0756 | mackenzie.lennon@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0128 / SECTION 2 3 LOT 128 | Exterior Doors (435401) (EXT) [7966414 - 76717518-000] [OP] | 5/19/2026 |  | $100.01 | $0.00 | $100.01 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0023 / PHASE 1 LOT 23 | GREEN PLATE MATERIAL (EXT) (411023) (MS03) [LS] [7966414 - 40980031-000] [OP] | 5/19/2026 |  | $835.11 | $81.42 | $916.53 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0024 / PHASE 1 LOT 24 | GREEN PLATE MATERIAL (EXT) (411023) (MS03) [LS] [7966414 - 33383634-000] [OP] | 5/19/2026 |  | $1,355.56 | $132.18 | $1,487.74 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0071 | Window Delivery and Install (423401) (INT) [7966414 - 75262751-000] [OP] | 5/20/2026 |  | $4,389.08 | $343.10 | $4,732.18 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0008 / PHASE 2 LOT 8 | Prefab Stairs (411801) (INT) [7966414 - 75266567-000] [OP] | 5/20/2026 |  | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0072 | Exterior Doors (435401) (EXT) [7966414 - 75264001-000] [OP] | 5/20/2026 |  | $100.02 | $0.00 | $100.02 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0072 | Window Delivery and Install (423401) (INT) [7966414 - 75263999-000] [OP] | 5/20/2026 |  | $4,413.87 | $343.56 | $4,757.43 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Symphony - 2235851 | 0071 | Exterior Doors (435401) (EXT) [7966414 - 75262769-000] [OP] | 5/20/2026 |  | $1,164.06 | $103.74 | $1,267.80 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0037 / PHASE 1 LOT 37 | Roof Trusses Delivery (411028) (EXT) [7966414 - 81980695-000] [OP] | 5/20/2026 |  | $4,835.28 | $471.44 | $5,306.72 | Mackenzie Lennon | (615) 856-0756 | mackenzie.lennon@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0010 / PHASE 2 LOT 10 | Prefab Stairs (411801) (INT) [7966414 - 81978253-000] [OP] | 5/20/2026 |  | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0177 / SECTION 2 3 LOT 177 | Prefab Stairs (411801) (INT) [7966414 - 78514781-000] [OP] | 5/20/2026 |  | $740.18 | $72.17 | $812.35 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0176 / SECTION 2 3 LOT 176 | Prefab Stairs (411801) (INT) [7966414 - 78513527-000] [OP] | 5/20/2026 |  | $740.18 | $72.17 | $812.35 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0035 / PHASE 1 LOT 35 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 28586306-000] [OP] | 5/21/2026 | 2/27/2026 | $4,057.20 | $395.58 | $4,452.78 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0008 | Prefab Stairs (411801) (INT) [LS] [7966414 - 46836014-000] [OP] | 5/21/2026 |  | $740.18 | $72.17 | $812.35 | Ken Clark | (661) 281-7143 | ken.clark@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0079 / PHASE 1 LOT 79 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 46829498-000] [OP] | 5/21/2026 |  | $4,037.69 | $306.88 | $4,344.57 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0167 / SECTION 2 3 LOT 167 | Window Delivery and Install (423401) (INT) [7966414 - 76706333-000] [OP] | 5/21/2026 |  | $5,524.14 | $435.73 | $5,959.87 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - The Oaks - 2238251 | 0209 / SECTION 2 LOT 209 | Window Delivery and Install (423401) (INT) [7966414 - 75272545-000] [OP] | 5/21/2026 |  | $4,448.38 | $348.87 | $4,797.25 | Scott Carrillo | (615) 854-2430 | scott.carrillo@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Cottage - 2236851 | 0014 | Roof Trusses Delivery (411028) (EXT) [7966414 - 85399072-000] [OP] | 5/21/2026 |  | $10,279.39 | $1,002.24 | $11,281.63 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Parkside - 2236751 | 0016 | Roof Trusses Delivery (411028) (EXT) [7966414 - 85394706-000] [OP] | 5/21/2026 |  | $12,054.98 | $1,175.36 | $13,230.34 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0418 / PHASE 2A LOT | Window Delivery and Install (423401) (INT) [7966414 - 85822213-000] [OP] | 5/21/2026 |  | $3,150.11 | $244.72 | $3,394.83 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0167 / SECTION 2 3 LOT 167 | Exterior Doors (435401) (EXT) [7966414 - 76706341-000] [OP] | 5/21/2026 |  | $671.00 | $55.67 | $726.67 | Brian Pierce | (629) 654-9198 | brian.pierce@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0024 / PHASE 1 LOT 24 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 33383651-000] [OP] | 5/22/2026 | 2/11/2026 | $4,988.98 | $486.43 | $5,475.41 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0024 / PHASE 1 LOT 24 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 33383669-000] [OP] | 5/22/2026 | 2/11/2026 | $3,175.18 | $309.58 | $3,484.76 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0023 / PHASE 1 LOT 23 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 40980058-000] [OP] | 5/22/2026 | 2/23/2026 | $4,440.38 | $432.94 | $4,873.32 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0023 / PHASE 1 LOT 23 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 40980066-000] [OP] | 5/22/2026 | 2/23/2026 | $4,635.60 | $451.96 | $5,087.56 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0366 / SECTION 2A LOT 366 | Window Delivery and Install (423401) (INT) [7966414 - 75271358-000] [OP] | 5/22/2026 |  | $3,784.60 | $289.03 | $4,073.63 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1008 | Window Delivery and Install (423401) (INT) [7966414 - 80528162-000] [OP] | 5/22/2026 |  | $14,308.83 | $1,107.43 | $15,416.26 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Vinewood - 3201251 | 1008 | Exterior Doors (435401) (EXT) [7966414 - 80528171-000] [OP] | 5/22/2026 |  | $3,720.86 | $314.03 | $4,034.89 | Steven Case | (615) 306-6613 | steven.case@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0037 / PHASE 1 LOT 37 | Prefab Stairs (411801) (INT) [7966414 - 81980724-000] [OP] | 5/22/2026 |  | $740.18 | $72.17 | $812.35 | Mackenzie Lennon | (615) 856-0756 | mackenzie.lennon@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0024 / PHASE 1 LOT 24 | Prefab Stairs (411801) (INT) [LS] [7966414 - 33383685-000] [OP] | 5/26/2026 |  | $740.18 | $72.17 | $812.35 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0010 / SECTION 1 PHASE 2 LOT 10 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 22712295-000] [OP] | 5/26/2026 |  | $3,496.69 | $271.68 | $3,768.37 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0023 / PHASE 1 LOT 23 | Prefab Stairs (411801) (INT) [LS] [7966414 - 40980082-000] [OP] | 5/26/2026 | 1/8/2026 | $740.18 | $72.17 | $812.35 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0025 / PHASE 1 LOT 25 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 40982248-000] [OP] | 5/26/2026 | 2/11/2026 | $8,125.22 | $792.21 | $8,917.43 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0048 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 43991852-000] [OP] | 5/26/2026 | 1/14/2026 | $3,175.18 | $309.58 | $3,484.76 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0078 / PHASE 5B | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 46729681-000] [OP] | 5/26/2026 | 1/13/2026 | $4,639.22 | $452.31 | $5,091.53 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0079 / PHASE 5B | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 46730957-000] [OP] | 5/26/2026 | 1/13/2026 | $4,480.90 | $436.89 | $4,917.79 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0050 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 46801284-000] [OP] | 5/26/2026 | 1/15/2026 | $4,639.22 | $452.31 | $5,091.53 | Ken Clark | (661) 281-7143 | ken.clark@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0048 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 43991844-000] [OP] | 5/26/2026 |  | $8,174.47 | $797.01 | $8,971.48 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0097 / LOT 97 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 44659915-000] [OP] | 5/26/2026 | 2/12/2026 | $3,424.56 | $333.89 | $3,758.45 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0098 / LOT 98 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 44662399-000] [OP] | 5/26/2026 | 2/12/2026 | $2,745.88 | $267.71 | $3,013.59 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0068 / SECTION 1 LOT 68 | Window Delivery and Install (423401) (INT) [7966414 - 75670391-000] [OP] | 5/26/2026 |  | $4,715.35 | $366.12 | $5,081.47 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0069 / SECTION 1 LOT 69 | Window Delivery and Install (423401) (INT) [7966414 - 75671669-000] [OP] | 5/26/2026 |  | $5,457.77 | $420.96 | $5,878.73 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0434 / PHASE 2 A LOT 434 | Window Delivery and Install (423401) (INT) [7966414 - 78517296-000] [OP] | 5/26/2026 |  | $2,123.71 | $166.59 | $2,290.30 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0443 / PHASE 2 A LOT 443 | Window Delivery and Install (423401) (INT) [7966414 - 85813325-000] [OP] | 5/26/2026 |  | $2,161.02 | $170.23 | $2,331.25 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0105 | Roof Trusses Delivery (411028) (EXT) [7966414 - 85816930-000] [OP] | 5/26/2026 |  | $4,991.06 | $486.63 | $5,477.69 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0068 / SECTION 1 LOT 68 | Exterior Doors (435401) (EXT) [7966414 - 75670404-000] [OP] | 5/26/2026 |  | $670.99 | $55.67 | $726.66 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0069 / SECTION 1 LOT 69 | Exterior Doors (435401) (EXT) [7966414 - 75671677-000] [OP] | 5/26/2026 |  | $670.99 | $55.67 | $726.66 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0078 / PHASE 5B | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 46729622-000] [OP] | 5/26/2026 |  | $9,746.64 | $950.34 | $10,696.98 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0079 / PHASE 5B | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 46730965-000] [OP] | 5/26/2026 |  | $3,311.48 | $322.88 | $3,634.36 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0079 / PHASE 5B | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 46730949-000] [OP] | 5/26/2026 |  | $18,396.94 | $1,793.72 | $20,190.66 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0078 / PHASE 5B | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 46729729-000] [OP] | 5/26/2026 |  | $1,737.82 | $169.45 | $1,907.27 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0048 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 43991861-000] [OP] | 5/26/2026 |  | $1,584.53 | $154.50 | $1,739.03 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0050 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 46801276-000] [OP] | 5/26/2026 |  | $9,016.87 | $879.16 | $9,896.03 | Ken Clark | (661) 281-7143 | ken.clark@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0050 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 46801292-000] [OP] | 5/26/2026 |  | $1,610.80 | $157.07 | $1,767.87 | Ken Clark | (661) 281-7143 | ken.clark@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0098 / LOT 98 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 44662410-000] [OP] | 5/26/2026 |  | $1,308.07 | $127.54 | $1,435.61 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0097 / LOT 97 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 44659798-000] [OP] | 5/26/2026 |  | $8,616.83 | $840.13 | $9,456.96 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0097 / LOT 97 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 44659923-000] [OP] | 5/26/2026 |  | $1,366.82 | $133.26 | $1,500.08 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0098 / LOT 98 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 44662217-000] [OP] | 5/26/2026 |  | $8,019.57 | $781.91 | $8,801.48 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0161 / PHASE 1B LOT 161 | Window Delivery and Install (423401) (INT) [7966414 - 72377755-000] [OP] | 5/27/2026 |  | $2,587.06 | $208.84 | $2,795.90 | Corey Burke | (615) 753-9159 | corey.burke@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Parkside Estates - 3200861 | 0020 | Window Delivery and Install (423401) (INT) [7966414 - 78520866-000] [OP] | 5/27/2026 |  | $3,150.11 | $244.72 | $3,394.83 | Quinton Miller | (615) 840-1839 | quinton.miller@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0160 / PHASE 1B LOT 160 | Window Delivery and Install (423401) (INT) [7966414 - 78516074-000] [OP] | 5/27/2026 |  | $3,528.60 | $268.94 | $3,797.54 | Ron Huckaby | (615) 630-5414 | Ron.Huckaby@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0008 / PHASE 2 LOT 8 | Window Delivery and Install (423401) (INT) [7966414 - 75266575-000] [OP] | 5/28/2026 |  | $5,258.04 | $410.25 | $5,668.29 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0010 / PHASE 2 LOT 10 | Window Delivery and Install (423401) (INT) [7966414 - 81978261-000] [OP] | 5/28/2026 |  | $4,536.29 | $348.67 | $4,884.96 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0573 / SECTION 2A LOT 573 | Window Delivery and Install (423401) (INT) [7966414 - 85807531-000] [OP] | 5/28/2026 |  | $3,528.60 | $268.94 | $3,797.54 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0572 / SECTION 2A LOT 572 | Window Delivery and Install (423401) (INT) [7966414 - 85804672-000] [OP] | 5/28/2026 |  | $3,959.81 | $313.91 | $4,273.72 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0034 / PHASE 1 LOT 34 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 33379643-000] [OP] | 5/29/2026 | 2/3/2026 | $2,345.16 | $185.74 | $2,530.90 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0048 | Prefab Stairs (411801) (INT) [LS] [7966414 - 43991879-000] [OP] | 5/29/2026 | 1/20/2026 | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0078 / PHASE 5B | Prefab Stairs (411801) (INT) [LS] [7966414 - 46729737-000] [OP] | 5/29/2026 |  | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0079 / PHASE 5B | Prefab Stairs (411801) (INT) [LS] [7966414 - 46730973-000] [OP] | 5/29/2026 |  | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0008 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 46836031-000] [OP] | 5/29/2026 |  | $5,463.83 | $421.56 | $5,885.39 | Ken Clark | (661) 281-7143 | ken.clark@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0050 | Prefab Stairs (411801) (INT) [LS] [7966414 - 46801305-000] [OP] | 5/29/2026 |  | $740.18 | $72.17 | $812.35 | Ken Clark | (661) 281-7143 | ken.clark@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0034 / PHASE 1 LOT 34 | Exterior Doors (435401) (EXT) [LS] [7966414 - 33379651-000] [OP] | 5/29/2026 |  | $779.01 | $66.20 | $845.21 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0012 / SECTION 1 PHASE 2 LOT 12 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 22714557-000] [OP] | 6/1/2026 | 2/2/2026 | $2,990.00 | $291.53 | $3,281.53 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0011 / SECTION 1 PHASE 2 LOT 11 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 22713407-000] [OP] | 6/1/2026 | 2/2/2026 | $3,385.60 | $330.10 | $3,715.70 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0012 / SECTION 1 PHASE 2 LOT 12 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 22714565-000] [OP] | 6/1/2026 | 2/2/2026 | $2,480.41 | $241.84 | $2,722.25 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0011 / SECTION 1 PHASE 2 LOT 11 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 22713415-000] [OP] | 6/1/2026 | 2/2/2026 | $2,843.90 | $277.29 | $3,121.19 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0037 / PHASE 1 LOT 37 | Window Delivery and Install (423401) (INT) [7966414 - 81980732-000] [OP] | 6/1/2026 |  | $5,473.95 | $426.91 | $5,900.86 | Mackenzie Lennon | (615) 856-0756 | mackenzie.lennon@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0016 / PHASE 2 LOT 16 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 82082061-000] [OP] | 6/1/2026 |  | $4,639.22 | $452.31 | $5,091.53 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0006 / PHASE 1B LOT 6 | Roof Trusses Delivery (411028) (EXT) [7966414 - 81979483-000] [OP] | 6/1/2026 |  | $4,034.46 | $393.36 | $4,427.82 | Ron Huckaby | (615) 630-5414 | Ron.Huckaby@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Cottage - 2236851 | 0015 | Window Delivery and Install (423401) (INT) [7966414 - 85399988-000] [OP] | 6/1/2026 |  | $11,262.32 | $891.83 | $12,154.15 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Cottage - 2236851 | 0015 | Exterior Doors (435401) (EXT) [7966414 - 85399996-000] [OP] | 6/1/2026 |  | $3,022.93 | $255.74 | $3,278.67 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0094 / Phase 5B | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 52875301-000] [OP] | 6/2/2026 |  | $4,639.22 | $452.31 | $5,091.53 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0176 / SECTION 2 3 LOT 176 | Window Delivery and Install (423401) (INT) [7966414 - 78513535-000] [OP] | 6/2/2026 |  | $5,457.77 | $420.96 | $5,878.73 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0177 / SECTION 2 3 LOT 177 | Window Delivery and Install (423401) (INT) [7966414 - 78514790-000] [OP] | 6/2/2026 |  | $5,472.32 | $426.76 | $5,899.08 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0176 / SECTION 2 3 LOT 176 | Exterior Doors (435401) (EXT) [7966414 - 78513543-000] [OP] | 6/2/2026 |  | $670.99 | $55.67 | $726.66 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0177 / SECTION 2 3 LOT 177 | Exterior Doors (435401) (EXT) [7966414 - 78514802-000] [OP] | 6/2/2026 |  | $670.99 | $55.67 | $726.66 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0078 / PHASE 1 LOT 78 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 44131934-000] [OP] | 6/3/2026 | 2/3/2026 | $4,194.24 | $408.94 | $4,603.18 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0011 / LOT 11 | Window Delivery and Install (423401) (INT) [7966414 - 75511551-000] [OP] | 6/3/2026 |  | $2,587.06 | $208.84 | $2,795.90 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0036 / PHASE 1 LOT 36 | Roof Trusses Delivery (411028) (EXT) [7966414 - 85840171-000] [OP] | 6/3/2026 |  | $4,360.14 | $425.12 | $4,785.26 | Mackenzie Lennon | (615) 856-0756 | mackenzie.lennon@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0036 / PHASE 1 LOT 36 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 85840180-000] [OP] | 6/3/2026 |  | $4,521.90 | $440.89 | $4,962.79 | Mackenzie Lennon | (615) 856-0756 | mackenzie.lennon@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0035 / PHASE 1 LOT 35 | Exterior Doors (435401) (EXT) [LS] [7966414 - 28586322-000] [OP] | 6/3/2026 |  | $778.99 | $66.20 | $845.19 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0035 / PHASE 1 LOT 35 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 28586314-000] [OP] | 6/4/2026 | 3/12/2026 | $2,622.11 | $212.26 | $2,834.37 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0036 / PHASE 1 LOT 36 | Prefab Stairs (411801) (INT) [7966414 - 85840219-000] [OP] | 6/4/2026 |  | $740.18 | $72.17 | $812.35 | Mackenzie Lennon | (615) 856-0756 | mackenzie.lennon@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0016 / PHASE 2 LOT 16 | Prefab Stairs (411801) (INT) [7966414 - 82082088-000] [OP] | 6/4/2026 |  | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Longview Classic - 3202951 | 0105 | Window Delivery and Install (423401) (INT) [7966414 - 85816964-000] [OP] | 6/4/2026 |  | $3,528.60 | $268.94 | $3,797.54 | Donald Sullivan | (615) 906-0962 | donald.sullivan@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0048 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 43991887-000] [OP] | 6/5/2026 |  | $4,715.35 | $366.12 | $5,081.47 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0079 / PHASE 5B | Window Delivery and Install (423401) (INT) [LS] [7966414 - 46730981-000] [OP] | 6/5/2026 | 1/26/2026 | $5,460.00 | $425.55 | $5,885.55 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0078 / PHASE 5B | Window Delivery and Install (423401) (INT) [LS] [7966414 - 46729745-000] [OP] | 6/5/2026 | 1/26/2026 | $5,463.83 | $421.56 | $5,885.39 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0050 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 46801313-000] [OP] | 6/5/2026 |  | $5,463.83 | $421.56 | $5,885.39 | Ken Clark | (661) 281-7143 | ken.clark@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0097 / LOT 97 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 44659931-000] [OP] | 6/5/2026 |  | $3,987.05 | $308.78 | $4,295.83 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0098 / LOT 98 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 44662428-000] [OP] | 6/5/2026 |  | $4,037.69 | $306.88 | $4,344.57 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0094 / Phase 5B | Prefab Stairs (411801) (INT) [LS] [7966414 - 52875327-000] [OP] | 6/5/2026 |  | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0024 / PHASE 1 LOT 24 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 33383693-000] [OP] | 6/8/2026 | 1/16/2026 | $4,715.35 | $366.12 | $5,081.47 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0023 / PHASE 1 LOT 23 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 40980091-000] [OP] | 6/8/2026 |  | $5,727.39 | $436.03 | $6,163.42 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0010 / LOT 10 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 43993524-000] [OP] | 6/8/2026 | 1/29/2026 | $3,227.94 | $314.73 | $3,542.67 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0436 / PHASE 2 A LOT 436 | Window Delivery and Install (423401) (INT) [7966414 - 78519654-000] [OP] | 6/8/2026 |  | $2,161.02 | $170.23 | $2,331.25 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Parkside - 2236751 | 0016 | Exterior Doors (435401) (EXT) [7966414 - 85394765-000] [OP] | 6/8/2026 |  | $2,976.69 | $251.23 | $3,227.92 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Cottage - 2236851 | 0014 | Exterior Doors (435401) (EXT) [7966414 - 85399208-000] [OP] | 6/8/2026 |  | $3,022.93 | $255.74 | $3,278.67 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Parkside - 2236751 | 0016 | Window Delivery and Install (423401) (INT) [7966414 - 85394757-000] [OP] | 6/8/2026 |  | $11,681.56 | $930.26 | $12,611.82 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Honey Farms Cottage - 2236851 | 0014 | Window Delivery and Install (423401) (INT) [7966414 - 85399161-000] [OP] | 6/8/2026 |  | $11,262.32 | $891.83 | $12,154.15 | Drew Sevier | (615) 714-6798 | drew.sevier@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0445 / PHASE 2 A LOT 445 | Window Delivery and Install (423401) (INT) [7966414 - 85815689-000] [OP] | 6/8/2026 |  | $2,117.17 | $165.95 | $2,283.12 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0444 / PHASE 2 A LOT 444 | Window Delivery and Install (423401) (INT) [7966414 - 85814521-000] [OP] | 6/8/2026 |  | $2,123.71 | $166.59 | $2,290.30 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0160 / SECTION 2 3 LOT 160 | Prefab Stairs (411801) (INT) [7966414 - 85792405-000] [OP] | 6/8/2026 |  | $740.18 | $72.17 | $812.35 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0025 / PHASE 1 LOT 25 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 40982301-000] [OP] | 6/9/2026 |  | $3,684.64 | $293.91 | $3,978.55 | Brittany Reid | (629) 273-2689 | brittany.reid@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0012 / SECTION 1 PHASE 2 LOT 12 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 22714602-000] [OP] | 6/9/2026 |  | $3,327.11 | $259.54 | $3,586.65 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0011 / SECTION 1 PHASE 2 LOT 11 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 22713458-000] [OP] | 6/9/2026 |  | $3,333.60 | $260.17 | $3,593.77 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0435 / PHASE 2 A LOT 435 | Window Delivery and Install (423401) (INT) [7966414 - 78518475-000] [OP] | 6/9/2026 | 5/22/2026 | $2,117.17 | $165.95 | $2,283.12 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Avery Trace - Classic - 2237851 | 0006 / PHASE 1B LOT 6 | Window Delivery and Install (423401) (INT) [7966414 - 81979491-000] [OP] | 6/10/2026 |  | $3,777.60 | $294.68 | $4,072.28 | Ron Huckaby | (615) 630-5414 | Ron.Huckaby@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0016 / PHASE 2 LOT 16 | Window Delivery and Install (423401) (INT) [7966414 - 82082096-000] [OP] | 6/11/2026 |  | $5,463.83 | $421.56 | $5,885.39 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0017 / PHASE 2 LOT 17 | Window Delivery and Install (423401) (INT) [7966414 - 82083347-000] [OP] | 6/11/2026 |  | $4,751.24 | $365.24 | $5,116.48 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0078 / PHASE 1 LOT 78 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 44131942-000] [OP] | 6/12/2026 |  | $3,784.60 | $289.03 | $4,073.63 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0094 / Phase 5B | Window Delivery and Install (423401) (INT) [LS] [7966414 - 52875335-000] [OP] | 6/12/2026 |  | $5,473.95 | $426.91 | $5,900.86 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0077 / PHASE 1 LOT 77 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 53115733-000] [OP] | 6/12/2026 |  | $4,124.82 | $315.38 | $4,440.20 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0025 / SECTION 1 PHASE 2 LOT 25 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 46828364-000] [OP] | 6/15/2026 | 1/28/2026 | $2,843.90 | $277.29 | $3,121.19 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0024 / SECTION 1 PHASE 2 LOT 24 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 53113287-000] [OP] | 6/15/2026 |  | $2,480.41 | $241.84 | $2,722.25 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0160 / SECTION 2 3 LOT 160 | Window Delivery and Install (423401) (INT) [7966414 - 85792413-000] [OP] | 6/15/2026 |  | $5,754.44 | $445.48 | $6,199.92 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0024 / SECTION 1 PHASE 2 LOT 24 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 53113156-000] [OP] | 6/15/2026 |  | $6,555.04 | $639.13 | $7,194.17 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0024 / SECTION 1 PHASE 2 LOT 24 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 53113332-000] [OP] | 6/15/2026 |  | $782.11 | $76.25 | $858.36 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0025 / SECTION 1 PHASE 2 LOT 25 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 46828348-000] [OP] | 6/15/2026 |  | $7,206.64 | $702.65 | $7,909.29 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0025 / SECTION 1 PHASE 2 LOT 25 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 46828372-000] [OP] | 6/15/2026 |  | $898.78 | $87.62 | $986.40 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0025 / SECTION 1 PHASE 2 LOT 25 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 46828356-000] [OP] | 6/16/2026 | 1/29/2026 | $3,317.89 | $323.49 | $3,641.38 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0024 / SECTION 1 PHASE 2 LOT 24 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 53113279-000] [OP] | 6/16/2026 |  | $2,840.04 | $276.90 | $3,116.94 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0013 / LOT 13 | Window Delivery and Install (423401) (INT) [7966414 - 82080875-000] [OP] | 6/16/2026 |  | $3,959.81 | $313.91 | $4,273.72 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Lisenbee Fields - 3202451 | 0119 / PHASE 1B LOT 119 | Window Delivery and Install (423401) (INT) [7966414 - 82088201-000] [OP] | 6/16/2026 |  | $3,333.60 | $260.17 | $3,593.77 | Gregg Tinnell | (629) 252-8336 | Gregg.Tinnell@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Lisenbee Fields - 3202451 | 0118 / PHASE 1B LOT 118 | Window Delivery and Install (423401) (INT) [7966414 - 82087065-000] [OP] | 6/16/2026 |  | $3,327.11 | $259.54 | $3,586.65 | Gregg Tinnell | (629) 252-8336 | Gregg.Tinnell@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Bowie Meadows - Reserve - 2239151 | 0036 / PHASE 1 LOT 36 | Window Delivery and Install (423401) (INT) [7966414 - 85840227-000] [OP] | 6/17/2026 |  | $5,460.00 | $425.55 | $5,885.55 | Mackenzie Lennon | (615) 856-0756 | mackenzie.lennon@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Dillon Pointe - 2235651 | 0010 / LOT 10 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 43993680-000] [OP] | 6/18/2026 |  | $3,959.81 | $313.91 | $4,273.72 | Rodney Thompson Jr | (615) 961-0234 | rodney.thompson@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Lisenbee Fields - 3202451 | 0120 / PHASE 1B LOT 120 | Window Delivery and Install (423401) (INT) [7966414 - 81981882-000] [OP] | 6/19/2026 |  | $2,345.16 | $185.74 | $2,530.90 | Gregg Tinnell | (629) 252-8336 | Gregg.Tinnell@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0009 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 47439483-000] [OP] | 6/22/2026 | 1/22/2026 | $4,480.90 | $436.89 | $4,917.79 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0097 / Phase 5B | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 72205224-000] [OP] | 6/22/2026 |  | $4,639.22 | $452.31 | $5,091.53 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Cambridge CORE - 2239761 | 0534 / PHASE 2A LOT 534 | Window Delivery and Install (423401) (INT) [7966414 - 85810087-000] [OP] | 6/22/2026 |  | $2,987.02 | $233.21 | $3,220.23 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0009 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 47439491-000] [OP] | 6/22/2026 |  | $1,648.94 | $160.78 | $1,809.72 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0009 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 47439475-000] [OP] | 6/22/2026 |  | $9,192.74 | $896.31 | $10,089.05 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0036 / PHASE 1 LOT 36 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 42782901-000] [OP] | 6/23/2026 |  | $4,147.36 | $404.37 | $4,551.73 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Knoll Creek - 2236251 | 0018 / PHASE 2 LOT 18 | Window Delivery and Install (423401) (INT) [7966414 - 85795796-000] [OP] | 6/24/2026 |  | $3,856.74 | $301.92 | $4,158.66 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0362 / SECTION 2A LOT 362 | Window Delivery and Install (423401) (INT) [7966414 - 85798671-000] [OP] | 6/24/2026 |  | $4,200.29 | $334.92 | $4,535.21 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms - Classic - 2238051 | 0363 / SECTION 2A LOT 363 | Window Delivery and Install (423401) (INT) [7966414 - 85801631-000] [OP] | 6/24/2026 |  | $3,448.41 | $263.06 | $3,711.47 | Justin Cota | (615) 736-1920 | justin.cota@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0025 / SECTION 1 PHASE 2 LOT 25 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 46828381-000] [OP] | 6/25/2026 | 2/9/2026 | $3,333.60 | $260.17 | $3,593.77 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0009 | Prefab Stairs (411801) (INT) [LS] [7966414 - 47439504-000] [OP] | 6/25/2026 |  | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Farmhouse Downs Cambridge - 2237251 | 0024 / SECTION 1 PHASE 2 LOT 24 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 53113341-000] [OP] | 6/25/2026 |  | $3,592.13 | $282.94 | $3,875.07 | Stefan Baumer | (629) 252-8174 | stefan.baumer@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0097 / Phase 5B | Prefab Stairs (411801) (INT) [7966414 - 72205241-000] [OP] | 6/25/2026 |  | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ross Farms Grandview Core - 2239861 | 0438 / PHASE 2 A LOT 438 | Window Delivery and Install (423401) (INT) [7966414 - 85811944-000] [OP] | 6/26/2026 |  | $2,319.13 | $181.26 | $2,500.39 | Ryan Duran | (555) 555-5555 | ryan.duran@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0047 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 46732186-000] [OP] | 6/29/2026 | 1/14/2026 | $4,480.90 | $436.89 | $4,917.79 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0046 | I-Joist Material 2nd Floor (411031) (INT) [7966414 - 72173154-000] [OP] | 6/29/2026 |  | $3,833.63 | $373.77 | $4,207.40 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0047 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 46732178-000] [OP] | 6/29/2026 |  | $8,730.28 | $851.20 | $9,581.48 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0047 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 46732194-000] [OP] | 6/29/2026 |  | $1,587.72 | $154.81 | $1,742.53 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0047 | Prefab Stairs (411801) (INT) [LS] [7966414 - 46732207-000] [OP] | 7/2/2026 |  | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0009 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 47439512-000] [OP] | 7/2/2026 | 2/3/2026 | $5,460.00 | $425.55 | $5,885.55 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Cambridge - 2237751 | 0036 / PHASE 1 LOT 36 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 42782910-000] [OP] | 7/2/2026 |  | $2,587.06 | $208.84 | $2,795.90 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Ashton Park - 3201351 | 0097 / Phase 5B | Window Delivery and Install (423401) (INT) [7966414 - 72205259-000] [OP] | 7/2/2026 |  | $5,754.44 | $445.48 | $6,199.92 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0046 | Prefab Stairs (411801) (INT) [7966414 - 72173293-000] [OP] | 7/2/2026 |  | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Spring Valley Estates - Classics - 2237651 | 0079 / PHASE 1 LOT 79 | Roof Trusses Delivery (411028) (EXT) [LS] [7966414 - 46829480-000] [OP] | 7/8/2026 |  | $4,060.57 | $395.91 | $4,456.48 | Terry Perry | (615) 968-1556 | terry.perry@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0047 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 46732215-000] [OP] | 7/10/2026 |  | $5,460.00 | $425.55 | $5,885.55 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Park - 3201451 | 0046 | Window Delivery and Install (423401) (INT) [7966414 - 72173349-000] [OP] | 7/10/2026 |  | $5,524.14 | $435.73 | $5,959.87 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0056 / SECTION 1 LOT 56 | Prefab Stairs (411801) (INT) [LS] [7966414 - 36378426-000] [OP] | 7/15/2026 | 2/10/2026 | $740.18 | $72.17 | $812.35 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0057 / SECTION 1 LOT 57 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 45977202-000] [OP] | 7/21/2026 | 2/17/2026 | $4,715.35 | $366.12 | $5,081.47 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Arbors of Compton - Reserve - 2235751 | 0056 / SECTION 1 LOT 56 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 36378445-000] [OP] | 7/27/2026 | 1/27/2026 | $6,115.42 | $489.50 | $6,604.92 | Robert Saso | (615) 708-3884 | robert.saso@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0010 | I-Joist Material 2nd Floor (411031) (INT) [LS] [7966414 - 48234720-000] [OP] | 7/27/2026 | 1/22/2026 | $4,794.24 | $467.43 | $5,261.67 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0010 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 48234738-000] [OP] | 7/27/2026 |  | $1,933.33 | $188.51 | $2,121.84 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0010 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 48234711-000] [OP] | 7/27/2026 |  | $9,458.74 | $922.23 | $10,380.97 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0010 | Prefab Stairs (411801) (INT) [LS] [7966414 - 48234746-000] [OP] | 7/30/2026 | 1/27/2026 | $740.18 | $72.17 | $812.35 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Wembley Estates - 3201551 | 0010 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 48234754-000] [OP] | 8/6/2026 |  | $5,727.39 | $436.03 | $6,163.42 | Steven Ware | (615) 426-9170 | steve.ware@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0072 / LOT 72 | LUMBER/HOUSEWRAP/SHEATHING (411007) (EXT) (MS03) [LS] [7966414 - 29977702-000] [OP] | 12/11/2026 | 2/11/2026 | $6,010.77 | $586.04 | $6,596.81 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0072 / LOT 72 | Roof Sheathing/Bracing/Hardware (411049) (EXT) [LS] [7966414 - 29977714-000] [OP] | 12/11/2026 | 2/11/2026 | $712.54 | $69.47 | $782.01 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0072 / LOT 72 | Frame Labor 1 (411205) (INT) [LS] [7966414 - 29977716-000] [OP] | 12/14/2026 | 2/12/2026 | $6,434.56 | $0.00 | $6,434.56 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete
Lennar - Nashville - NSH | NSH - Pleasant Grove - Cambridge - 2237451 | 0072 / LOT 72 | Window Delivery and Install (423401) (INT) [LS] [7966414 - 29977741-000] [OP] | 12/28/2026 | 2/25/2026 | $4,034.86 | $328.56 | $4,363.42 | Lisa Ward | (615) 207-2686 | lisa.ward@lennar.com | Incomplete