## SupplyPro Orders
Builder Name | Subdivision | Lot / Block | Task | Requested Start Date | Actual Start Date | Subtotal | Tax | Total | Contact Name | Contact Phone | Contact Email | Status
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0016 / 000 | DELIVER INTERIOR TRIM/DOOR PACKAGE [2850233 - 17864800-000] [LC] | 4/27/2026 |  | $4,562.67 | $444.87 | $5,007.54 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0016 / 000 | INSTALL INTERIOR TRIM [2850233 - 17864801-000] [LC] | 4/28/2026 |  | $1,989.12 | $0.00 | $1,989.12 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0014 / 000 | DELIVER INTERIOR TRIM/DOOR PACKAGE [2850233 - 17838506-000] [LC] | 4/29/2026 |  | $3,508.37 | $342.07 | $3,850.44 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0015 / 000 | DELIVER INTERIOR TRIM/DOOR PACKAGE [2850233 - 17816186-000] [LC] | 4/29/2026 |  | $4,562.67 | $444.87 | $5,007.54 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0014 / 000 | INSTALL INTERIOR TRIM [2850233 - 17838507-000] [LC] | 4/30/2026 |  | $1,314.00 | $0.00 | $1,314.00 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0015 / 000 | INSTALL INTERIOR TRIM [2850233 - 17816187-000] [LC] | 4/30/2026 |  | $1,989.12 | $0.00 | $1,989.12 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0020 / 000 | DELIVER INTERIOR TRIM/DOOR PACKAGE [2850233 - 17969705-000] [LC] | 5/12/2026 |  | $0.00 | $0.00 | $0.00 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0020 / 000 | INSTALL INTERIOR TRIM [2850233 - 17969706-000] [LC] | 5/13/2026 |  | $0.00 | $0.00 | $0.00 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0016 / 000 | TRIM FINAL AND SHOE MOLDING | 5/13/2026 |  | $0.00 | $0.00 | $0.00 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0014 / 000 | TRIM FINAL AND SHOE MOLDING | 5/14/2026 |  | $0.00 | $0.00 | $0.00 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0015 / 000 | TRIM FINAL AND SHOE MOLDING | 5/14/2026 |  | $0.00 | $0.00 | $0.00 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0020 / 000 | DELIVER INTERIOR TRIM/DOOR PACKAGE [2850233 - 18088608-000] [LC] | 5/29/2026 |  | $5,002.81 | $487.76 | $5,490.57 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0021 / 000 | DELIVER INTERIOR TRIM/DOOR PACKAGE [2850233 - 17960481-000] [LC] | 6/1/2026 |  | $4,768.19 | $464.91 | $5,233.10 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0020 / 000 | INSTALL INTERIOR TRIM [2850233 - 18088609-000] [LC] | 6/1/2026 |  | $1,942.47 | $0.00 | $1,942.47 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0021 / 000 | INSTALL INTERIOR TRIM [2850233 - 17960482-000] [LC] | 6/2/2026 |  | $1,754.88 | $0.00 | $1,754.88 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0027 / 000 | DELIVER INTERIOR TRIM/DOOR PACKAGE [2850233 - 18083956-000] [LC] | 7/2/2026 |  | $5,193.44 | $506.36 | $5,699.80 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0027 / 000 | INSTALL INTERIOR TRIM [2850233 - 18083957-000] [LC] | 7/6/2026 |  | $2,288.52 | $0.00 | $2,288.52 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0022 / 000 | DELIVER INTERIOR TRIM/DOOR PACKAGE [2850233 - 18048625-000] [LC] | 7/13/2026 |  | $5,193.44 | $506.36 | $5,699.80 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete
M/I Homes, Inc. - Nashville Division - ,1213 | 285102000000 Pennington Mills | 0022 / 000 | INSTALL INTERIOR TRIM [2850233 - 18048626-000] [LC] | 7/14/2026 |  | $2,289.03 | $0.00 | $2,289.03 | Adam Wallace | (330) 903-0015 | awallace@mihomes.com | Incomplete