## SupplyPro Orders
Builder Name | Subdivision | Lot / Block | Task | Requested Start Date | Actual Start Date | Subtotal | Tax | Total | Contact Name | Contact Phone | Contact Email | Status
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | River Ridge 50's (LN) | 0050 | Shoe Molding and Trim Final Punch [372412 - 12397294-000 - 51040][TO] [A] | 4/2/2026 |  | $0.00 | $0.00 | $0.00 | Andy Bardeen | (931) 378-1289 | Andy.Bardeen@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | River Ridge 50's (LN) | 0077 | Shoe Molding and Trim Final Punch [372412 - 12391349-000 - 51040][TO] [A] | 4/2/2026 |  | $0.00 | $0.00 | $0.00 | Andy Bardeen | (931) 378-1289 | Andy.Bardeen@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Station Hill 65' SF | 0036 | Warranty-Window [372412 - 1753786-000 - 80100][OW] [A] | 4/3/2026 |  | $0.00 | $0.00 | $0.00 | Arthur Orr | (530) 574-1239 | Arthur.Orr@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0115 | Delay Fee [372412 - 2401138-000 - 51020][OH] [A] | 4/7/2026 |  | ($450.00) | $0.00 | ($450.00) | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H9 | Deliver Floor Joists [372412 - 92245-000 - 34100][LC] [A] | 4/8/2026 |  | $3,831.38 | $0.00 | $3,831.38 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H9 | Deliver Box Stairs [372412 - 12543205-000 - 50070][TO] [A] | 4/8/2026 |  | $1,215.00 | $118.46 | $1,333.46 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H9 | Deliver Trusses [372412 - 92245-000 - 34140][LC] [A] | 4/8/2026 |  | $2,531.13 | $0.00 | $2,531.13 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H9 | Deliver Loose Lumber [372412 - 12543202-000 - 34030][TO] [A] | 4/8/2026 |  | $10,277.90 | $1,000.23 | $11,278.13 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | Deliver Floor Joists [372412 - 92093-000 - 34100][LC] [A] | 4/10/2026 |  | $3,831.38 | $0.00 | $3,831.38 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | Deliver Loose Lumber [372412 - 12543113-000 - 34030][TO] [A] | 4/10/2026 |  | $10,515.44 | $1,023.40 | $11,538.84 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | Deliver Trusses [372412 - 92093-000 - 34140][LC] [A] | 4/10/2026 |  | $2,846.84 | $0.00 | $2,846.84 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | Deliver Box Stairs [372412 - 12543116-000 - 50070][TO] [A] | 4/10/2026 |  | $1,215.00 | $118.46 | $1,333.46 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H47 | EPO: 04/13/2026 [372412 - 2405039-000 - 36020][OH] [A] | 4/13/2026 |  | $321.30 | $0.00 | $321.30 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H35 | EPO: 04/13/2026 [372412 - 2405035-000 - 36020][OH] [A] | 4/13/2026 |  | $321.30 | $0.00 | $321.30 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H4 | EPO: 04/13/2026 [372412 - 2405036-000 - 36020][OH] [A] | 4/13/2026 |  | $321.30 | $0.00 | $321.30 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | HS | EPO: 04/13/2026 [372412 - 2405043-000 - 36020][OH] [A] | 4/13/2026 |  | $321.30 | $0.00 | $321.30 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H49 | EPO: 04/13/2026 [372412 - 2405040-000 - 36020][OH] [A] | 4/13/2026 |  | $321.30 | $0.00 | $321.30 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H9 | EPO: 04/13/2026 [372412 - 2405042-000 - 36020][OH] [A] | 4/13/2026 |  | $321.30 | $0.00 | $321.30 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H35 | EPO: 04/13/2026 [372412 - 2405307-000 - 36020][OH] [A] | 4/13/2026 |  | $48.39 | $0.00 | $48.39 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | Lumber Fill In Order [372412 - 12581525-000 - 34020][TO] [A] | 4/14/2026 |  | $269.33 | $26.26 | $295.59 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 51' (LN) | 0047 | provide and install window screens $344.33 [372412 - 2405792-000 - 35020][OH] [A] | 4/14/2026 |  | $344.33 | $0.00 | $344.33 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 51' (LN) | 0052 | provide and install window screens $344.33 [372412 - 2405810-000 - 35020][OH] [A] | 4/14/2026 |  | $344.33 | $0.00 | $344.33 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 51' (LN) | 0041 | provide and install window screens $344.33 [372412 - 2405801-000 - 35020][OH] [A] | 4/14/2026 |  | $344.33 | $0.00 | $344.33 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0100 | Screens [372412 - 2401007-000 - 51020][OH] [A] | 4/15/2026 |  | $344.18 | $0.00 | $344.18 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Briarcreek 50' (Cane Ridge LN) | 0052 | Cost for window screens $344.65 [372412 - 2405935-000 - 64270][OH] [A] | 4/15/2026 |  | $344.73 | $0.00 | $344.73 | Britt Greer | (615) 925-1737 | chandler.greer@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H41 | EPO: 04/13/2026 [372412 - 2405037-000 - 36020][OH] [A] | 4/17/2026 |  | $321.30 | $0.00 | $321.30 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H47 | EPO: 04/13/2026 [372412 - 2405310-000 - 36020][OH] [A] | 4/17/2026 |  | $48.39 | $0.00 | $48.39 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | EPO: 04/13/2026 [372412 - 2405312-000 - 36020][OH] [A] | 4/17/2026 |  | $48.39 | $0.00 | $48.39 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H4 | EPO: 04/13/2026 [372412 - 2405306-000 - 36020][OH] [A] | 4/17/2026 |  | $48.39 | $0.00 | $48.39 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | HS | EPO: 04/13/2026 [372412 - 2405314-000 - 36020][OH] [A] | 4/17/2026 |  | $48.39 | $0.00 | $48.39 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H9 | EPO: 04/13/2026 [372412 - 2405313-000 - 36020][OH] [A] | 4/17/2026 |  | $48.39 | $0.00 | $48.39 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H41 | EPO: 04/13/2026 [372412 - 2405308-000 - 36020][OH] [A] | 4/17/2026 |  | $48.39 | $0.00 | $48.39 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H43 | EPO: 04/13/2026 [372412 - 2405309-000 - 36020][OH] [A] | 4/17/2026 |  | $48.39 | $0.00 | $48.39 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H43 | EPO: 04/10/2026 [372412 - 2404826-000 - 36020][OH] [A] | 4/17/2026 |  | $321.30 | $0.00 | $321.30 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H49 | EPO: 04/13/2026 [372412 - 2405311-000 - 36020][OH] [A] | 4/17/2026 |  | $48.39 | $0.00 | $48.39 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | EPO: 04/13/2026 [372412 - 2405041-000 - 36020][OH] [A] | 4/20/2026 |  | $321.30 | $0.00 | $321.30 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0161 | Warranty-Trim Carpentry [372412 - 1759043-000 - 80055][OW] [A] | 4/20/2026 |  | $0.00 | $0.00 | $0.00 | Brian Blackburn | (615) 804-2641 | brian.blackburn@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | The Reserve | 316 | Struct Int - MHC Costs [372412 - 1760013-000 - 81610][OW] [A] | 4/20/2026 |  | $0.00 | $0.00 | $0.00 | Zach Baker | (555) 555-5555 | zach.baker@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0159 | Warranty-Trim Carpentry [372412 - 1760019-000 - 80055][OW] [A] | 4/20/2026 |  | $0.00 | $0.00 | $0.00 | Brian Blackburn | (615) 804-2641 | brian.blackburn@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0114 | Shoe Molding and Trim Final Punch [372412 - 11733795-000 - 51040][TO] [A] | 4/21/2026 |  | $137.75 | $0.00 | $137.75 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0198 | Frame Inspection | 4/21/2026 |  | $0.00 | $0.00 | $0.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0197 | Frame Inspection | 4/21/2026 |  | $0.00 | $0.00 | $0.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0196 | Frame Inspection | 4/21/2026 |  | $0.00 | $0.00 | $0.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0195 | Frame Inspection | 4/21/2026 |  | $0.00 | $0.00 | $0.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0194 | Frame Inspection | 4/21/2026 |  | $0.00 | $0.00 | $0.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0183 | Windows [372412 - 12564123-000 - 36020][TO] [A] | 4/22/2026 |  | $1.00 | $0.00 | $1.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0183 | Windows [372412 - 160746-000 - 36020][LC] [A] | 4/22/2026 |  | $3,880.92 | $0.00 | $3,880.92 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0183 | Exterior Doors [372412 - 12564124-000 - 37020][TO] [A] | 4/22/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0184 | Frame Labor [372412 - 12563934-000 - 35020][TO] [A] | 4/22/2026 |  | $8,196.20 | $0.00 | $8,196.20 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Station Hill 75' SF | 0012 | Shoe Molding and Trim Final Punch [372412 - 12332039-000 - 51040][TO] [A] | 4/22/2026 |  | $156.25 | $14.45 | $170.70 | Chase Ford |  | Chase.Ford@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 51' (LN) | 0050 | Shoe Molding and Trim Final Punch [372412 - 12404141-000 - 51040][TO] [A] | 4/22/2026 |  | $91.75 | $0.00 | $91.75 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0185 | Frame Labor [372412 - 12574968-000 - 35020][TO] [A] | 4/22/2026 |  | $7,452.65 | $0.00 | $7,452.65 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0186 | Frame Labor [372412 - 12575063-000 - 35020][TO] [A] | 4/22/2026 |  | $8,428.40 | $0.00 | $8,428.40 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Wyncliff 52' (LN) | 0088 | window repair and screens BC $400 [372412 - 2407782-000 - 34030][OH] [A] | 4/22/2026 |  | $400.00 | $0.00 | $400.00 | Andy Bardeen | (931) 378-1289 | Andy.Bardeen@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 51' (LN) | 0052 | replace broken upper sash $276.15 [372412 - 2407610-000 - 35020][OH] [A] | 4/23/2026 |  | $276.15 | $0.00 | $276.15 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Briarcreek 50' (Cane Ridge LN) | 0160 | Warranty-Trim Carpentry [372412 - 1759140-000 - 80055][OW] [A] | 4/23/2026 |  | $0.00 | $0.00 | $0.00 | Britt Greer | (615) 925-1737 | chandler.greer@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H2 | Windows [372412 - 12535397-000 - 36020][TO] [A] | 4/24/2026 |  | $1.00 | $0.00 | $1.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H2 | Exterior Doors [372412 - 12535398-000 - 37020][TO] [A] | 4/24/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Station Hill 75' SF | 0011 | Install Window Screens | 4/24/2026 |  | $0.00 | $0.00 | $0.00 | Chase Ford |  | Chase.Ford@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Station Hill 75' SF | 0020 | Install Window Screens | 4/24/2026 |  | $0.00 | $0.00 | $0.00 | Chase Ford |  | Chase.Ford@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0186 | Deliver Loose Lumber [372412 - 12625756-000 - 34030][TO] [A] | 4/24/2026 |  | $10,882.21 | $1,057.34 | $11,939.55 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0114 | Threshold Repair [372412 - 2406267-000 - 37020][OH] [A] | 4/27/2026 |  | $58.00 | $0.00 | $58.00 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | Exterior Doors [372412 - 12543115-000 - 37020][TO] [A] | 4/28/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | Windows [372412 - 12543114-000 - 36020][TO] [A] | 4/28/2026 |  | $1.00 | $0.00 | $1.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | Windows [372412 - 92122-000 - 36020][LC] [A] | 4/28/2026 |  | $3,733.10 | $0.00 | $3,733.10 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H9 | Windows [372412 - 12543203-000 - 36020][TO] [A] | 4/28/2026 |  | $1.00 | $0.00 | $1.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H9 | Windows [372412 - 92261-000 - 36020][LC] [A] | 4/28/2026 |  | $3,733.10 | $0.00 | $3,733.10 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H9 | Exterior Doors [372412 - 12543204-000 - 37020][TO] [A] | 4/28/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H46 | Shoe Molding and Trim Final Punch [372412 - 12460365-000 - 51040][TO] [A] | 4/28/2026 |  | $117.60 | $0.00 | $117.60 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H47 | Shoe Molding and Trim Final Punch [372412 - 12485872-000 - 51040][TO] [A] | 4/28/2026 |  | $87.45 | $0.00 | $87.45 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0191 | Frame Punchout - Retention [372412 - 12558185-000 - 35040][TO] [A] | 4/28/2026 |  | $1,000.00 | $0.00 | $1,000.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0192 | Frame Punchout - Retention [372412 - 12558277-000 - 35040][TO] [A] | 4/28/2026 |  | $1,000.00 | $0.00 | $1,000.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0187 | Deliver Floor Joists [372412 - 325213-000 - 34100][LC] [A] | 4/28/2026 |  | $5,208.00 | $0.00 | $5,208.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0188 | Deliver Floor Joists [372412 - 325361-000 - 34100][LC] [A] | 4/28/2026 |  | $3,410.31 | $0.00 | $3,410.31 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0188 | Deliver Loose Lumber [372412 - 12614700-000 - 34030][TO] [A] | 4/28/2026 |  | $10,882.21 | $1,057.34 | $11,939.55 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0187 | Deliver Loose Lumber [372412 - 12614796-000 - 34030][TO] [A] | 4/28/2026 |  | $10,190.56 | $993.58 | $11,184.14 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0188 | Deliver Loose Lumber [372412 - 12616006-000 - 34030][TO] [A] | 4/28/2026 |  | $869.40 | $84.77 | $954.17 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0187 | Deliver Loose Lumber [372412 - 12616007-000 - 34030][TO] [A] | 4/28/2026 |  | $841.75 | $82.07 | $923.82 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0193 | Frame Punchout - Retention [372412 - 12551128-000 - 35040][TO] [A] | 4/28/2026 |  | $1,000.00 | $0.00 | $1,000.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0209 | Warranty-Trim Carpentry [372412 - 1761091-000 - 80055][OW] [A] | 4/28/2026 |  | $0.00 | $0.00 | $0.00 | Brian Blackburn | (615) 804-2641 | brian.blackburn@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0184 | Exterior Doors [372412 - 12563937-000 - 37020][TO] [A] | 4/29/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0184 | Windows [372412 - 12563936-000 - 36020][TO] [A] | 4/29/2026 |  | $1.00 | $0.00 | $1.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0184 | Windows [372412 - 160607-000 - 36020][LC] [A] | 4/29/2026 |  | $3,403.34 | $0.00 | $3,403.34 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0185 | Exterior Doors [372412 - 12574971-000 - 37020][TO] [A] | 4/29/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0185 | Windows [372412 - 12574970-000 - 36020][TO] [A] | 4/29/2026 |  | $1.00 | $0.00 | $1.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0185 | Windows [372412 - 194612-000 - 36020][LC] [A] | 4/29/2026 |  | $3,298.52 | $0.00 | $3,298.52 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0186 | Windows [372412 - 194751-000 - 36020][LC] [A] | 4/29/2026 |  | $3,880.92 | $0.00 | $3,880.92 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0186 | Exterior Doors [372412 - 12575066-000 - 37020][TO] [A] | 4/29/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0186 | Windows [372412 - 12575065-000 - 36020][TO] [A] | 4/29/2026 |  | $1.00 | $0.00 | $1.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0113 | Rear door threshold repair [372412 - 2406264-000 - 37020][OH] [A] | 4/29/2026 |  | $75.42 | $0.00 | $75.42 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0112 | Back door replace [372412 - 2406262-000 - 37020][OH] [A] | 4/29/2026 |  | $591.18 | $0.00 | $591.18 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0115 | Threshold repair [372412 - 2406268-000 - 37020][OH] [A] | 4/29/2026 |  | $83.00 | $0.00 | $83.00 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Station Hill 75' SF | 0149 | Install Window Screens | 4/29/2026 |  | $0.00 | $0.00 | $0.00 | Chase Ford |  | Chase.Ford@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0187 | Deliver Trusses [372412 - 325213-000 - 34140][LC] [A] | 4/29/2026 |  | $2,992.57 | $0.00 | $2,992.57 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0188 | Deliver Trusses [372412 - 325361-000 - 34140][LC] [A] | 4/29/2026 |  | $3,846.43 | $0.00 | $3,846.43 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0188 | Frame Labor [372412 - 12616006-000 - 35020][TO] [A] | 4/29/2026 |  | $8,428.40 | $0.00 | $8,428.40 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0189 | Deliver Floor Joists [372412 - 337214-000 - 34100][LC] [A] | 4/29/2026 |  | $5,208.00 | $0.00 | $5,208.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0187 | Frame Labor [372412 - 12616007-000 - 35020][TO] [A] | 4/29/2026 |  | $8,196.20 | $0.00 | $8,196.20 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0190 | Deliver Floor Joists [372412 - 337361-000 - 34100][LC] [A] | 4/29/2026 |  | $4,278.00 | $0.00 | $4,278.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0100 | Deliver Floor Joists [372412 - 343884-000 - 34100][LC] [A] | 4/29/2026 |  | $4,016.67 | $0.00 | $4,016.67 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0183 | Frame Punchout - Retention [372412 - 12564122-000 - 35040][TO] [A] | 4/29/2026 |  | $1,000.00 | $0.00 | $1,000.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0100 | Deliver Loose Lumber [372412 - 12621421-000 - 34030][TO] [A] | 4/29/2026 |  | $8,624.96 | $839.09 | $9,464.05 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0189 | Deliver Loose Lumber [372412 - 12619691-000 - 34030][TO] [A] | 4/29/2026 |  | $10,222.00 | $996.65 | $11,218.65 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0190 | Deliver Loose Lumber [372412 - 12619596-000 - 34030][TO] [A] | 4/29/2026 |  | $9,340.88 | $908.90 | $10,249.78 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0052 | Warranty-Ext Doors & Windows [372412 - 1760584-000 - 80105][OW] [A] | 4/29/2026 |  | $0.00 | $0.00 | $0.00 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H4 | Interior Trim Material [372412 - 99951849-000 - 50060][LC] [A] | 4/30/2026 |  | $3,241.93 | $316.09 | $3,558.02 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0115 | Screens [372412 - 2400676-000 - 35020][OH] [A] | 4/30/2026 |  | $344.18 | $0.00 | $344.18 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0114 | screens [372412 - 2400675-000 - 35020][OH] [A] | 4/30/2026 |  | $344.18 | $0.00 | $344.18 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0112 | window screens [372412 - 2400670-000 - 34030][OH] [A] | 4/30/2026 |  | $344.18 | $0.00 | $344.18 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0190 | Deliver Trusses [372412 - 337361-000 - 34140][LC] [A] | 4/30/2026 |  | $2,842.91 | $0.00 | $2,842.91 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0189 | Deliver Trusses [372412 - 337214-000 - 34140][LC] [A] | 4/30/2026 |  | $2,942.68 | $0.00 | $2,942.68 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0100 | Deliver Trusses [372412 - 343884-000 - 34140][LC] [A] | 4/30/2026 |  | $2,543.67 | $0.00 | $2,543.67 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0190 | Frame Labor [372412 - 12619597-000 - 35020][TO] [A] | 4/30/2026 |  | $7,452.65 | $0.00 | $7,452.65 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0189 | Frame Labor [372412 - 12619692-000 - 35020][TO] [A] | 4/30/2026 |  | $8,196.20 | $0.00 | $8,196.20 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0100 | Frame Labor [372412 - 12621422-000 - 35020][TO] [A] | 4/30/2026 |  | $6,660.50 | $0.00 | $6,660.50 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 40' (LN) | 32 | Deliver Floor Joists [372412 - 356520-000 - 34100][LC] [A] | 4/30/2026 |  | $6,045.00 | $0.00 | $6,045.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 40' (LN) | 32 | Deliver Box Stairs [372412 - 12625761-000 - 50070][TO] [A] | 4/30/2026 |  | $1,215.00 | $118.46 | $1,333.46 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 40' (LN) | 32 | Deliver Trusses [372412 - 356520-000 - 34140][LC] [A] | 4/30/2026 |  | $4,054.92 | $0.00 | $4,054.92 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 40' (LN) | 32 | Deliver Loose Lumber [372412 - 12625758-000 - 34030][TO] [A] | 4/30/2026 |  | $11,678.31 | $1,123.82 | $12,802.13 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Briarcreek 60' (Cane Ridge LN) | 0237 | Warranty-Trim Carpentry [372412 - 1761726-000 - 80055][OW] [A] | 4/30/2026 |  | $0.00 | $0.00 | $0.00 | Britt Greer | (615) 925-1737 | chandler.greer@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Poplar Farms (Ingraham) - MTH | 0113 | window screens [372412 - 2400673-000 - 34030][OH] [A] | 5/1/2026 |  | $382.15 | $0.00 | $382.15 | Jeff Pennell | (615) 660-4111 | Jeff.Pennell@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H4 | Trim Labor [372412 - 12495472-000 - 51020][TO] [A] | 5/1/2026 |  | $961.95 | $0.00 | $961.95 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0194 | Frame Punchout - Retention [372412 - 12523652-000 - 35040][TO] [A] | 5/2/2026 |  | $1,000.00 | $0.00 | $1,000.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0195 | Frame Punchout - Retention [372412 - 12523745-000 - 35040][TO] [A] | 5/2/2026 |  | $1,000.00 | $0.00 | $1,000.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0196 | Frame Punchout - Retention [372412 - 12523839-000 - 35040][TO] [A] | 5/2/2026 |  | $1,000.00 | $0.00 | $1,000.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0197 | Frame Punchout - Retention [372412 - 12523932-000 - 35040][TO] [A] | 5/2/2026 |  | $1,000.00 | $0.00 | $1,000.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0198 | Frame Punchout - Retention [372412 - 12524026-000 - 35040][TO] [A] | 5/2/2026 |  | $1,000.00 | $0.00 | $1,000.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Station Hill 75' SF | 0012 | Install Window Screens | 5/4/2026 |  | $0.00 | $0.00 | $0.00 | Chase Ford |  | Chase.Ford@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 40' (LN) | 32 | Windows [372412 - 12625759-000 - 36020][TO] [A] | 5/5/2026 |  | $1.00 | $0.00 | $1.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 40' (LN) | 32 | Windows [372412 - 356546-000 - 36020][LC] [A] | 5/5/2026 |  | $4,776.68 | $0.00 | $4,776.68 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 40' (LN) | 32 | Exterior Doors [372412 - 12625760-000 - 37020][TO] [A] | 5/5/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0187 | Windows [372412 - 325230-000 - 36020][LC] [A] | 5/6/2026 |  | $3,403.34 | $0.00 | $3,403.34 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0187 | Windows [372412 - 12614797-000 - 36020][TO] [A] | 5/6/2026 |  | $1.00 | $0.00 | $1.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0187 | Exterior Doors [372412 - 12614798-000 - 37020][TO] [A] | 5/6/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0188 | Windows [372412 - 325387-000 - 36020][LC] [A] | 5/6/2026 |  | $3,880.92 | $0.00 | $3,880.92 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0188 | Windows [372412 - 12614701-000 - 36020][TO] [A] | 5/6/2026 |  | $1.00 | $0.00 | $1.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0188 | Exterior Doors [372412 - 12614702-000 - 37020][TO] [A] | 5/6/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0190 | Windows [372412 - 12619599-000 - 36020][TO] [A] | 5/7/2026 |  | $1.00 | $0.00 | $1.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0189 | Windows [372412 - 337231-000 - 36020][LC] [A] | 5/7/2026 |  | $3,403.34 | $0.00 | $3,403.34 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0190 | Windows [372412 - 337388-000 - 36020][LC] [A] | 5/7/2026 |  | $3,279.89 | $0.00 | $3,279.89 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0189 | Exterior Doors [372412 - 12619695-000 - 37020][TO] [A] | 5/7/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0189 | Windows [372412 - 12619694-000 - 36020][TO] [A] | 5/7/2026 |  | $1.00 | $0.00 | $1.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0190 | Exterior Doors [372412 - 12619600-000 - 37020][TO] [A] | 5/7/2026 |  | $1,482.50 | $128.95 | $1,611.45 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0100 | Windows [372412 - 343905-000 - 36020][LC] [A] | 5/7/2026 |  | $2,501.17 | $0.00 | $2,501.17 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0100 | Windows [372412 - 12621424-000 - 36020][TO] [A] | 5/7/2026 |  | $1.00 | $0.00 | $1.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0100 | Exterior Doors [372412 - 12621425-000 - 37020][TO] [A] | 5/7/2026 |  | $1,105.78 | $92.22 | $1,198.00 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0170 | Warranty-Framing [372412 - 1758998-000 - 80050][OW] [A] | 5/7/2026 |  | $0.00 | $0.00 | $0.00 | Brian Blackburn | (615) 804-2641 | brian.blackburn@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0170 | Warranty-Trim Carpentry [372412 - 1759000-000 - 80055][OW] [A] | 5/7/2026 |  | $0.00 | $0.00 | $0.00 | Brian Blackburn | (615) 804-2641 | brian.blackburn@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0159 | Warranty-Framing [372412 - 1759502-000 - 80050][OW] [A] | 5/7/2026 |  | $0.00 | $0.00 | $0.00 | Brian Blackburn | (615) 804-2641 | brian.blackburn@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0159 | Warranty-Framing [372412 - 1759504-000 - 80050][OW] [A] | 5/7/2026 |  | $0.00 | $0.00 | $0.00 | Brian Blackburn | (615) 804-2641 | brian.blackburn@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | HS | Install Window Screens | 5/8/2026 |  | $0.00 | $0.00 | $0.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H47 | Install Window Screens | 5/8/2026 |  | $0.00 | $0.00 | $0.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H42 | Interior Trim Material [372412 - 39049-000 - 50060][LC] [A] | 5/11/2026 |  | $3,151.82 | $307.30 | $3,459.12 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H41 | Interior Trim Material [372412 - 68616-000 - 50060][LC] [A] | 5/11/2026 |  | $3,241.93 | $316.09 | $3,558.02 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Briarcreek 60' (Cane Ridge LN) | 0238 | Interior Trim Material [372412 - 30079-000 - 50060][LC] [A] | 5/11/2026 |  | $4,016.64 | $391.62 | $4,408.26 | Britt Greer | (615) 925-1737 | chandler.greer@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H42 | Trim Labor [372412 - 12521340-000 - 51020][TO] [A] | 5/12/2026 |  | $1,293.60 | $0.00 | $1,293.60 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H4 | Shoe Molding and Trim Final Punch [372412 - 12495473-000 - 51040][TO] [A] | 5/12/2026 |  | $87.45 | $0.00 | $87.45 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H41 | Trim Labor [372412 - 12535489-000 - 51020][TO] [A] | 5/12/2026 |  | $961.95 | $0.00 | $961.95 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H46 | Install Window Screens | 5/13/2026 |  | $0.00 | $0.00 | $0.00 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0194 | Interior Trim Material [372412 - 41659-000 - 50060][LC] [A] | 5/13/2026 |  | $3,581.13 | $349.16 | $3,930.29 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0195 | Interior Trim Material [372412 - 41860-000 - 50060][LC] [A] | 5/13/2026 |  | $3,241.93 | $316.09 | $3,558.02 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0196 | Interior Trim Material [372412 - 42011-000 - 50060][LC] [A] | 5/13/2026 |  | $3,241.93 | $316.09 | $3,558.02 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0197 | Interior Trim Material [372412 - 42192-000 - 50060][LC] [A] | 5/13/2026 |  | $3,581.13 | $349.16 | $3,930.29 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Crestview 41' (LN) | 0198 | Interior Trim Material [372412 - 42336-000 - 50060][LC] [A] | 5/13/2026 |  | $3,581.13 | $349.16 | $3,930.29 | Trevor Newsom | (615) 663-3897 | trevor.newsom@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H2 | Interior Trim Material [372412 - 68472-000 - 50060][LC] [A] | 5/15/2026 |  | $3,151.82 | $307.30 | $3,459.12 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H7 | Interior Trim Material [372412 - 92157-000 - 50060][LC] [A] | 5/15/2026 |  | $3,241.93 | $316.09 | $3,558.02 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H9 | Interior Trim Material [372412 - 92296-000 - 50060][LC] [A] | 5/15/2026 |  | $3,241.93 | $316.09 | $3,558.02 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 30' (LN) | H42 | Shoe Molding and Trim Final Punch [372412 - 12521341-000 - 51040][TO] [A] | 5/20/2026 |  | $117.60 | $0.00 | $117.60 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 40' (LN) | 32 | Interior Trim Material [372412 - 356571-000 - 50060][LC] [A] | 5/26/2026 |  | $3,954.40 | $385.55 | $4,339.95 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete
Meritage Homes - 835 NASHVILLE HBA - ,1202,1280 | Avery Farms 40' (LN) | 32 | Trim Labor [372412 - 12625762-000 - 51020][TO] [A] | 5/27/2026 |  | $1,370.05 | $0.00 | $1,370.05 | Nick Dellavalle | (000) 000-0000 | nick.dellavalle@meritagehomes.com | Incomplete