## Schedules
Builder | Subdivision | Lot # | Title | Scheduled Date | Project Manager
Ole South Properties | BLU | 12 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-04-27 | Jacob Gordon
Ole South Properties | BLU | 104 | FRAME PKG DELIVERY (Ole South Properties) | 2026-04-27 | Jacob Gordon
Ole South Properties | HOB | 5 | FRAME PKG DELIVERY (Ole South Properties) | 2026-04-27 | Alex Weldon
Ole South Properties | BLU | 104 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-04-28 | Jacob Gordon
Ole South Properties | SFM | 74 | FRAME PKG DELIVERY (Ole South Properties) | 2026-04-29 | Pat Murphy
Ole South Properties | BLU | 105 | FRAME PKG DELIVERY (Ole South Properties) | 2026-04-30 | Jacob Gordon
Ole South Properties | RFB | 182 | FRAME PKG DELIVERY (Ole South Properties) | 2026-04-30 | Steve Holliday
Ole South Properties | SWD | 13 | FRAME PKG DELIVERY (Ole South Properties) | 2026-04-30 | David Melvin, Pat Murphy
Ole South Properties | BLU | 105 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-05-01 | Jacob Gordon
Ole South Properties | SFM | 43 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-01 | Pat Murphy
Ole South Properties | WHF | 145 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-01 | David Melvin
Ole South Properties | BWS | 236 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-04 | Jacob Gordon
Ole South Properties | BWS | 237 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-04 | Jacob Gordon
Ole South Properties | RFB | 183 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-04 | Steve Holliday
Ole South Properties | BWS | 236 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-05-05 | Jacob Gordon
Ole South Properties | BWS | 237 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-05-05 | Jacob Gordon
Ole South Properties | CMB | 199 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-06 | Peter Willems
Ole South Properties | HOB | 15 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-06 | Alex Weldon
Ole South Properties | RFB | 184 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-06 | Steve Holliday
Ole South Properties | BRB | 124 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-07 | Gary Case
Ole South Properties | SLS | 270 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-07 | Danny Bradford
Ole South Properties | SLS | 270 | Roof Truss Delivery (Ole South Properties) | 2026-05-07 | Danny Bradford
Ole South Properties | STO | 15 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-07 | Pat Murphy
Ole South Properties | CMB | 206 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-08 | Peter Willems
Ole South Properties | PSN | 8 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-08 | Shawn Watson
Ole South Properties | RFB | 186 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-08 | Steve Holliday
Ole South Properties | BLU | 11 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-11 | Jacob Gordon
Ole South Properties | HOB | 18 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-11 | Alex Weldon
Ole South Properties | RIC | 1B | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-11 | Ethan Hein
Ole South Properties | SFM | 70 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-11 | Pat Murphy
Ole South Properties | BLU | 11 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-05-12 | Jacob Gordon
Ole South Properties | BPT | 73 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-12 | Shawn Watson
Ole South Properties | RFB | 194 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-12 | Steve Holliday
Ole South Properties | STO | 88 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-12 | Pat Murphy
Ole South Properties | SLS | 325 | Roof Truss Delivery (Ole South Properties) | 2026-05-13 | Danny Bradford
Ole South Properties | SLS | 325 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-13 | Danny Bradford
Ole South Properties | BPT | 72 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-14 | Shawn Watson
Ole South Properties | RFB | 210 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-14 | Steve Holliday
Ole South Properties | RKB | 40 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-14 | Alex Weldon
Ole South Properties | SWD | 17 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-15 | Pat Murphy
Ole South Properties | BWS | 230 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | Jacob Gordon
Ole South Properties | BWS | 232 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | Jacob Gordon
Ole South Properties | BWS | 240 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | Jacob Gordon
Ole South Properties | PAR | 10A | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | David Melvin
Ole South Properties | PAR | 10B | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | David Melvin
Ole South Properties | PAR | 10C | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | David Melvin
Ole South Properties | PAR | 10D | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | David Melvin
Ole South Properties | PAR | 10E | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | David Melvin
Ole South Properties | PAR | 10F | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | David Melvin
Ole South Properties | PAR | 10G | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | David Melvin
Ole South Properties | PAR | 10H | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | David Melvin
Ole South Properties | VCV | 42 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | Nick Baker
Ole South Properties | VCV | 43 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | Nick Baker
Ole South Properties | VCV | 44 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-18 | Nick Baker
Ole South Properties | BWS | 230 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-05-19 | Jacob Gordon
Ole South Properties | BWS | 232 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-05-19 | Jacob Gordon
Ole South Properties | BWS | 240 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-05-19 | Jacob Gordon
Ole South Properties | HOB | 13 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-19 | Alex Weldon
Ole South Properties | SLS | 334 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-19 | Danny Bradford
Ole South Properties | SLS | 334 | Roof Truss Delivery (Ole South Properties) | 2026-05-19 | Danny Bradford
Ole South Properties | SWD | 14 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-19 | Pat Murphy
Ole South Properties | RIC | 2B | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-20 | Ethan Hein
Ole South Properties | RKB | 23 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-20 | Alex Weldon
Ole South Properties | BLU | 9 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-21 | Jacob Gordon
Ole South Properties | BLU | 10 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-21 | Jacob Gordon
Ole South Properties | BLU | 9 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-05-22 | Jacob Gordon
Ole South Properties | BLU | 10 | ROOF TRUSS DELIVERY (Ole South Properties) | 2026-05-22 | Jacob Gordon
Ole South Properties | HOB | 12 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-22 | Alex Weldon
Ole South Properties | STR | 42 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-22 | Pat Murphy
Ole South Properties | RKB | 24 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-26 | Alex Weldon
Ole South Properties | HOB | 11 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-27 | Alex Weldon
Ole South Properties | STR | 45 | FRAME PKG DELIVERY (Ole South Properties) | 2026-05-27 | David Melvin, Pat Murphy
Ole South Properties | STR | 52 | FRAME PKG DELIVERY (Ole South Properties) | 2026-06-01 | David Melvin, Pat Murphy
Ole South Properties | SLS | 356 | Roof Truss Delivery (Ole South Properties) | 2026-06-08 | Danny Bradford
Ole South Properties | SLS | 356 | FRAME PKG DELIVERY (Ole South Properties) | 2026-06-08 | Danny Bradford