## SupplyPro Orders
Builder Name | Subdivision | Lot / Block | Task | Requested Start Date | Actual Start Date | Subtotal | Tax | Total | Contact Name | Contact Phone | Contact Email | Status
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0185 | Window Material and Install [1152547 _ 41884451-136 _ 5250-11][ON] | 4/2/2026 |  | $5,844.43 | $0.00 | $5,844.43 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0003 | Window Material and Install [1152547 _ 83792861-015 _ 5250-11][ON] | 4/3/2026 |  | $18,640.90 | $0.00 | $18,640.90 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0003 | Exterior Door Install [1152547 _ 83792861-015 _ 5260-31][ON] | 4/3/2026 |  | $1,172.50 | $0.00 | $1,172.50 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0141 | Framing 1st Draw [1152547 _ 41884538-102 _ 5220-21][ON] | 4/9/2026 |  | $0.00 | $0.00 | $0.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0186 | Int. Trim/Mill [1152547 _ 41884451-137 _ 5640-11][ON] | 4/13/2026 |  | $7,838.48 | $0.00 | $7,838.48 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0029 | Window Material and Install [1152547 _ 41884451-014 _ 5250-11][ON] | 4/14/2026 |  | $7,058.00 | $0.00 | $7,058.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0029 | Exterior Doors Install [1152547 _ 41884451-014 _ 5260-31][ON] | 4/14/2026 |  | $1,823.69 | $0.00 | $1,823.69 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0134 | Weather Barrier House Wrap [1152547 _ 41884538-095 _ 5240-11][ON] | 4/15/2026 |  | $865.00 | $0.00 | $865.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0139 | Framing 1st Draw [1152547 _ 41884538-100 _ 5220-21][ON] | 4/15/2026 |  | $15,274.47 | $0.00 | $15,274.47 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0139 | Panels 1st Drop [1152547 _ 41884538-100 _ 5220-14][ON] | 4/15/2026 |  | $15,011.48 | $0.00 | $15,011.48 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0134 | Window Material and Install [1152547 _ 41884451-095 _ 5250-11][ON] | 4/16/2026 |  | $5,844.43 | $0.00 | $5,844.43 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0134 | Exterior Doors Install [1152547 _ 41884451-095 _ 5260-31][ON] | 4/16/2026 |  | $1,823.69 | $0.00 | $1,823.69 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0139 | Drop Floor System [1152547 _ 41884554-100 _ 5210-11][ON] | 4/17/2026 |  | $4,850.00 | $0.00 | $4,850.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Meadowlark Radnor Collection | 0065 | Screens | 4/20/2026 |  | $0.00 | $0.00 | $0.00 | Vanessa VanCleve | (629) 251-0909 | VVanCleve@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0131 | Int. Trim/Mill [1152547 _ 41884565-060 _ 5640-11][ON] | 4/20/2026 |  | $21,488.33 | $0.00 | $21,488.33 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0043 | Framing 1st Draw [1152547 _ 41884566-041 _ 5220-21][ON] | 4/21/2026 |  | $20,732.34 | $0.00 | $20,732.34 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0043 | Panels 1st Drop [1152547 _ 41884566-041 _ 5220-14][ON] | 4/21/2026 |  | $14,909.31 | $0.00 | $14,909.31 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0139 | Roof Truss [1152547 _ 41884554-100 _ 5230-11][ON] | 4/22/2026 |  | $6,455.18 | $0.00 | $6,455.18 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0043 | Drop Floor System [1152547 _ 41884569-041 _ 5210-11][ON] | 4/23/2026 |  | $5,388.00 | $0.00 | $5,388.00 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0013 | Window Material and Install [1152547 _ 83792861-019 _ 5250-11][ON] | 4/24/2026 |  | $0.00 | $0.00 | $0.00 | System Admin | (215) 938-8000 | test@test.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0013 | Exterior Door Install [1152547 _ 83792861-019 _ 5260-31][ON] | 4/24/2026 |  | $0.00 | $0.00 | $0.00 | System Admin | (215) 938-8000 | test@test.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0180 | Framing 1st Draw [1152547 _ 41884538-131 _ 5220-21][ON] | 4/24/2026 |  | $15,719.48 | $0.00 | $15,719.48 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0180 | Panels 1st Drop [1152547 _ 41884538-131 _ 5220-14][ON] | 4/24/2026 |  | $15,456.49 | $0.00 | $15,456.49 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Meadowlark Radnor Collection | 0066 | Screens | 4/27/2026 |  | $0.00 | $0.00 | $0.00 | Vanessa VanCleve | (629) 251-0909 | VVanCleve@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0043 | Roof Truss [1152547 _ 41884569-041 _ 5230-11][ON] | 4/28/2026 |  | $8,255.00 | $0.00 | $8,255.00 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0180 | Drop Floor System [1152547 _ 41884554-131 _ 5210-11][ON] | 4/28/2026 |  | $4,850.00 | $0.00 | $4,850.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0025 | Window Material and Install [1152547 _ 41884565-037 _ 5250-11][ON] | 4/29/2026 |  | $10,848.54 | $0.00 | $10,848.54 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0139 | Weather Barrier House Wrap [1152547 _ 41884538-100 _ 5240-11][ON] | 4/30/2026 |  | $865.00 | $0.00 | $865.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0025 | Exterior Doors Install [1152547 _ 41884565-037 _ 5260-31][ON] | 5/1/2026 |  | $1,120.65 | $0.00 | $1,120.65 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0025 | Sliding Glass Door [1152547 _ 41884565-037 _ 5250-12][ON] | 5/1/2026 |  | $1,570.00 | $0.00 | $1,570.00 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0180 | Roof Truss [1152547 _ 41884554-131 _ 5230-11][ON] | 5/1/2026 |  | $6,455.18 | $0.00 | $6,455.18 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0009 | Window Material and Install [1152547 _ 83792861-022 _ 5250-11][ON] | 5/1/2026 |  | $14,786.55 | $0.00 | $14,786.55 | System Admin | (215) 938-8000 | test@test.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0009 | Exterior Door Install [1152547 _ 83792861-022 _ 5260-31][ON] | 5/1/2026 |  | $1,172.50 | $0.00 | $1,172.50 | System Admin | (215) 938-8000 | test@test.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0135 | Framing 1st Draw [1152547 _ 41884538-096 _ 5220-21][ON] | 5/5/2026 |  | $15,805.68 | $0.00 | $15,805.68 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0135 | Drop Floor System [1152547 _ 41884554-096 _ 5210-11][ON] | 5/5/2026 |  | $5,944.00 | $0.00 | $5,944.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0135 | Panels 1st Drop [1152547 _ 41884538-096 _ 5220-14][ON] | 5/5/2026 |  | $15,145.86 | $0.00 | $15,145.86 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0138 | Framing 1st Draw [1152547 _ 41884538-099 _ 5220-21][ON] | 5/5/2026 |  | $14,608.01 | $0.00 | $14,608.01 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0138 | Drop Floor System [1152547 _ 41884554-099 _ 5210-11][ON] | 5/5/2026 |  | $7,400.00 | $0.00 | $7,400.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0138 | Panels 1st Drop [1152547 _ 41884538-099 _ 5220-14][ON] | 5/5/2026 |  | $13,190.94 | $0.00 | $13,190.94 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0043 | Weather Barrier House Wrap [1152547 _ 41884566-041 _ 5240-11][ON] | 5/6/2026 |  | $865.00 | $0.00 | $865.00 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0135 | Roof Truss [1152547 _ 41884554-096 _ 5230-11][ON] | 5/7/2026 |  | $10,255.18 | $0.00 | $10,255.18 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0142 | Framing 1st Draw [1152547 _ 41884538-103 _ 5220-21][ON] | 5/7/2026 |  | $14,608.02 | $0.00 | $14,608.02 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0142 | Panels 1st Drop [1152547 _ 41884538-103 _ 5220-14][ON] | 5/7/2026 |  | $13,190.95 | $0.00 | $13,190.95 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0138 | Roof Truss [1152547 _ 41884554-099 _ 5230-11][ON] | 5/7/2026 |  | $7,732.20 | $0.00 | $7,732.20 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0139 | Window Material and Install [1152547 _ 41884451-100 _ 5250-11][ON] | 5/7/2026 |  | $9,061.66 | $0.00 | $9,061.66 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0139 | Exterior Doors Install [1152547 _ 41884451-100 _ 5260-31][ON] | 5/7/2026 |  | $1,120.65 | $0.00 | $1,120.65 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0178 | Framing 1st Draw [1152547 _ 41884538-129 _ 5220-21][ON] | 5/7/2026 |  | $14,608.02 | $0.00 | $14,608.02 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0178 | Panels 1st Drop [1152547 _ 41884538-129 _ 5220-14][ON] | 5/7/2026 |  | $13,190.95 | $0.00 | $13,190.95 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0013 | Exterior Door Install [1152547 _ 83792861-019 _ 5260-31][ON] | 5/7/2026 |  | $1,172.50 | $0.00 | $1,172.50 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0013 | Window Material and Install [1152547 _ 83792861-019 _ 5250-11][ON] | 5/7/2026 |  | $21,785.53 | $0.00 | $21,785.53 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0135 | Weather Barrier House Wrap [1152547 _ 41884538-096 _ 5240-11][ON] | 5/8/2026 |  | $865.00 | $0.00 | $865.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0138 | Weather Barrier House Wrap [1152547 _ 41884538-099 _ 5240-11][ON] | 5/8/2026 |  | $865.00 | $0.00 | $865.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0135 | Window Material and Install [1152547 _ 41884451-096 _ 5250-11][ON] | 5/11/2026 |  | $9,937.01 | $0.00 | $9,937.01 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0135 | Exterior Doors Install [1152547 _ 41884451-096 _ 5260-31][ON] | 5/11/2026 |  | $1,826.98 | $0.00 | $1,826.98 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0142 | Drop Floor System [1152547 _ 41884554-103 _ 5210-11][ON] | 5/11/2026 |  | $7,400.00 | $0.00 | $7,400.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0138 | Window Material and Install [1152547 _ 41884451-099 _ 5250-11][ON] | 5/11/2026 |  | $5,844.43 | $0.00 | $5,844.43 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0138 | Exterior Doors Install [1152547 _ 41884451-099 _ 5260-31][ON] | 5/11/2026 |  | $1,823.69 | $0.00 | $1,823.69 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0139 | Sliding Glass Door [1152547 _ 41884451-100 _ 5250-12][ON] | 5/11/2026 |  | $1,570.00 | $0.00 | $1,570.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0178 | Drop Floor System [1152547 _ 41884554-129 _ 5210-11][ON] | 5/11/2026 |  | $7,400.00 | $0.00 | $7,400.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0180 | Weather Barrier House Wrap [1152547 _ 41884538-131 _ 5240-11][ON] | 5/11/2026 |  | $865.00 | $0.00 | $865.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0043 | Window Material and Install [1152547 _ 41884565-041 _ 5250-11][ON] | 5/13/2026 |  | $12,500.41 | $0.00 | $12,500.41 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0043 | Exterior Doors Install [1152547 _ 41884565-041 _ 5260-31][ON] | 5/13/2026 |  | $2,271.30 | $0.00 | $2,271.30 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0142 | Roof Truss [1152547 _ 41884554-103 _ 5230-11][ON] | 5/14/2026 |  | $7,732.20 | $0.00 | $7,732.20 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0178 | Roof Truss [1152547 _ 41884554-129 _ 5230-11][ON] | 5/14/2026 |  | $7,732.20 | $0.00 | $7,732.20 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0043 | Sliding Glass Door [1152547 _ 41884565-041 _ 5250-12][ON] | 5/15/2026 |  | $5,600.00 | $0.00 | $5,600.00 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0180 | Window Material and Install [1152547 _ 41884451-131 _ 5250-11][ON] | 5/18/2026 |  | $6,061.18 | $0.00 | $6,061.18 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0180 | Exterior Doors Install [1152547 _ 41884451-131 _ 5260-31][ON] | 5/18/2026 |  | $1,117.65 | $0.00 | $1,117.65 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Meadowlark Radnor Collection | 0063 | Screens | 5/18/2026 |  | $0.00 | $0.00 | $0.00 | Vanessa VanCleve | (629) 251-0909 | VVanCleve@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0180 | Sliding Glass Door [1152547 _ 41884451-131 _ 5250-12][ON] | 5/20/2026 |  | $4,800.00 | $0.00 | $4,800.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0010 | Exterior Door Install [1152547 _ 83792861-020 _ 5260-31][ON] | 5/20/2026 |  | $1,172.50 | $0.00 | $1,172.50 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0010 | Window Material and Install [1152547 _ 83792861-020 _ 5250-11][ON] | 5/20/2026 |  | $13,971.04 | $0.00 | $13,971.04 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | August Park | 0110 | Framing 1st Draw [1152547 _ 15575218-027 _ 5220-21][ON] | 5/21/2026 |  | $22,155.04 | $0.00 | $22,155.04 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | August Park | 0110 | Panels 1st Drop [1152547 _ 15575218-027 _ 5220-14][ON] | 5/21/2026 |  | $24,539.51 | $0.00 | $24,539.51 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0142 | Weather Barrier House Wrap [1152547 _ 41884538-103 _ 5240-11][ON] | 5/26/2026 |  | $865.00 | $0.00 | $865.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0178 | Weather Barrier House Wrap [1152547 _ 41884538-129 _ 5240-11][ON] | 5/26/2026 |  | $865.00 | $0.00 | $865.00 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | August Park | 0110 | Drop Floor System [1152547 _ 15575218-027 _ 5210-11][ON] | 5/27/2026 |  | $14,332.23 | $0.00 | $14,332.23 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | August Park | 0110 | Roof Truss [1152547 _ 15575218-027 _ 5230-11][ON] | 6/1/2026 |  | $9,512.03 | $0.00 | $9,512.03 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0142 | Window Material and Install [1152547 _ 41884451-103 _ 5250-11][ON] | 6/2/2026 |  | $5,844.43 | $0.00 | $5,844.43 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0142 | Exterior Doors Install [1152547 _ 41884451-103 _ 5260-31][ON] | 6/2/2026 |  | $1,823.69 | $0.00 | $1,823.69 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0178 | Window Material and Install [1152547 _ 41884451-129 _ 5250-11][ON] | 6/2/2026 |  | $8,524.54 | $0.00 | $8,524.54 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0178 | Exterior Doors Install [1152547 _ 41884451-129 _ 5260-31][ON] | 6/2/2026 |  | $1,826.98 | $0.00 | $1,826.98 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | August Park | 0110 | Frame 3 Cornice [1152547 _ 15575218-027 _ 5220-23][ON] | 6/4/2026 |  | $2,299.12 | $0.00 | $2,299.12 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0025 | Main Stairs Turnkey [1152547 _ 41884566-037 _ 5602-31][ON] | 6/12/2026 |  | $1,415.01 | $0.00 | $1,415.01 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0025 | Int. Trim/Mill [1152547 _ 41884565-037 _ 5640-11][ON] | 6/15/2026 |  | $12,405.91 | $0.00 | $12,405.91 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | August Park | 0110 | Window Material and Install [1152547 _ 15575218-027 _ 5250-11][ON] | 6/16/2026 |  | $11,970.79 | $0.00 | $11,970.79 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | August Park | 0110 | Exterior Doors Install [1152547 _ 15575218-027 _ 5260-31][ON] | 6/16/2026 |  | $920.08 | $0.00 | $920.08 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0029 | Main Stairs Turnkey [1152547 _ 41884538-014 _ 5602-31][ON] | 6/19/2026 |  | $1,415.01 | $0.00 | $1,415.01 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0029 | Int. Trim/Mill [1152547 _ 41884451-014 _ 5640-11][ON] | 6/22/2026 |  | $12,199.06 | $0.00 | $12,199.06 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0138 | Main Stairs Turnkey [1152547 _ 41884538-099 _ 5602-31][ON] | 6/22/2026 |  | $1,415.01 | $0.00 | $1,415.01 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0139 | Main Stairs Turnkey [1152547 _ 41884538-100 _ 5602-31][ON] | 6/22/2026 |  | $1,415.01 | $0.00 | $1,415.01 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0138 | Int. Trim/Mill [1152547 _ 41884451-099 _ 5640-11][ON] | 6/23/2026 |  | $7,269.38 | $0.00 | $7,269.38 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0139 | Int. Trim/Mill [1152547 _ 41884451-100 _ 5640-11][ON] | 6/23/2026 |  | $9,474.56 | $0.00 | $9,474.56 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0141 | Int. Trim/Mill [1152547 _ 41884451-102 _ 5640-11][ON] | 6/25/2026 |  | $3,222.43 | $0.00 | $3,222.43 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0007 | Exterior Door Install [1152547 _ 83792861-018 _ 5260-31][ON] | 6/25/2026 |  | $1,172.50 | $0.00 | $1,172.50 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0007 | Window Material and Install [1152547 _ 83792861-018 _ 5250-11][ON] | 6/25/2026 |  | $13,132.21 | $0.00 | $13,132.21 | Shawn Mulligan | (629) 772-2690 | SMulligan@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0043 | Main Stairs Turnkey [1152547 _ 41884566-041 _ 5602-31][ON] | 6/26/2026 |  | $1,415.01 | $0.00 | $1,415.01 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-50' SFD | 0043 | Int. Trim/Mill [1152547 _ 41884565-041 _ 5640-11][ON] | 6/29/2026 |  | $23,458.77 | $0.00 | $23,458.77 | Daniel Marchetti | (770) 518-4896 | DMarchetti@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0134 | Main Stairs Turnkey [1152547 _ 41884538-095 _ 5602-31][ON] | 7/1/2026 |  | $1,415.01 | $0.00 | $1,415.01 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0180 | Main Stairs Turnkey [1152547 _ 41884538-131 _ 5602-31][ON] | 7/1/2026 |  | $1,415.01 | $0.00 | $1,415.01 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0134 | Int. Trim/Mill [1152547 _ 41884451-095 _ 5640-11][ON] | 7/2/2026 |  | $8,578.41 | $0.00 | $8,578.41 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0180 | Int. Trim/Mill [1152547 _ 41884451-131 _ 5640-11][ON] | 7/2/2026 |  | $9,474.56 | $0.00 | $9,474.56 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0142 | Main Stairs Turnkey [1152547 _ 41884538-103 _ 5602-31][ON] | 7/15/2026 |  | $1,415.01 | $0.00 | $1,415.01 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0178 | Main Stairs Turnkey [1152547 _ 41884538-129 _ 5602-31][ON] | 7/15/2026 |  | $1,415.01 | $0.00 | $1,415.01 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0142 | Int. Trim/Mill [1152547 _ 41884451-103 _ 5640-11][ON] | 7/16/2026 |  | $7,545.96 | $0.00 | $7,545.96 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0178 | Int. Trim/Mill [1152547 _ 41884451-129 _ 5640-11][ON] | 7/16/2026 |  | $8,578.41 | $0.00 | $8,578.41 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | August Park | 0131 | Window Material and Install [1152547 _ 15575218-023 _ 5250-11][ON] | 7/16/2026 |  | $16,319.15 | $0.00 | $16,319.15 | System Admin | (215) 938-8000 | test@test.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | August Park | 0131 | Exterior Doors Install [1152547 _ 15575218-023 _ 5260-31][ON] | 7/16/2026 |  | $920.08 | $0.00 | $920.08 | System Admin | (215) 938-8000 | test@test.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0135 | Main Stairs Turnkey [1152547 _ 41884538-096 _ 5602-31][ON] | 7/22/2026 |  | $1,415.01 | $0.00 | $1,415.01 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Tomlinson Pointe-40' SFD | 0135 | Int. Trim/Mill [1152547 _ 41884451-096 _ 5640-11][ON] | 7/23/2026 |  | $9,936.16 | $0.00 | $9,936.16 | Jonathan Huston | (623) 694-5651 | JHuston@tollbrothers.com | Incomplete
Toll Brothers Inc. E1 - Tennessee - ,1202 | Franklin Ridge | 0008 | Window Material and Install [1152547 _ 83792861-021 _ 5250-11][ON] | 8/6/2026 |  | $12,105.10 | $0.00 | $12,105.10 | System Admin | (215) 938-8000 | test@test.com | Incomplete